## product backlog
PRODUCT BACKLOG
BACKLOG ITEM
SPRINT BACKLOG | US ID | AS A/AN | I WANT TO | SO THAT | PRIORITY | RESPONSIBLE | ESTIMATE DATE | REMARKS
1 | SB1/US1 | Frontend Team | Implement Guardian Verification | So that the Frontend Team can benefit from guardian verification | 3 | Frontend Team | 2026-01-02 | Storage
1 | SB1/US2 | Admin | Implement Schedule Delivery | So that the Admin can benefit from schedule delivery | 3 | Admin | 2025-09-22 | Storage
1 | SB1/US3 | User | Implement Encryption Implementation | So that the User can benefit from encryption implementation | 3 | User | 2025-10-06 | Compliance
1 | SB1/US4 | Guardian | Implement Upload Media | So that the Guardian can benefit from upload media | 3 | Guardian | 2025-11-16 | Storage
1 | SB1/US5 | Admin | Implement Create Capsule | So that the Admin can benefit from create capsule | 3 | Admin | 2025-09-23 | Notification
1 | SB1/US6 | User | Implement Biometric Alive Check | So that the User can benefit from biometric alive check | 1 | User | 2025-12-30 | Testing
1 | SB1/US7 | Frontend Team | Implement Cloud Integration | So that the Frontend Team can benefit from cloud integration | 2 | Frontend Team | 2025-09-27 | Storage
1 | SB1/US8 | DevOps | Implement Premium Subscription Setup | So that the DevOps can benefit from premium subscription setup | 2 | DevOps | 2026-03-10 | Notification
1 | SB1/US9 | Legal Advisor | Implement Create Capsule | So that the Legal Advisor can benefit from create capsule | 2 | Legal Advisor | 2025-12-05 | UI/UX
1 | SB1/US10 | Admin | Implement Voice/Video Support | So that the Admin can benefit from voice/video support | 1 | Admin | 2026-03-14 | Notification
1 | SB1/US11 | Admin | Implement User Dashboard | So that the Admin can benefit from user dashboard | 1 | Admin | 2026-02-21 | Testing
1 | SB1/US12 | Security Team | Implement Create Capsule | So that the Security Team can benefit from create capsule | 3 | Security Team | 2026-01-30 | Deployment
1 | SB1/US13 | Legal Advisor | Implement Role Management | So that the Legal Advisor can benefit from role management | 2 | Legal Advisor | 2025-12-28 | Testing
1 | SB1/US14 | Backend Team | Implement Upload Media | So that the Backend Team can benefit from upload media | 1 | Backend Team | 2025-10-03 | Notification
1 | SB1/US15 | User | Implement Premium Subscription Setup | So that the User can benefit from premium subscription setup | 2 | User | 2025-10-30 | Deployment
1 | SB1/US1 | Guardian | Implement Role Management | So that the Guardian can benefit from role management | 2 | Guardian | 2026-03-01 | Authentication
1 | SB1/US2 | Frontend Team | Implement Freemium Model Setup | So that the Frontend Team can benefit from freemium model setup | 2 | Frontend Team | 2026-03-16 | Storage
1 | SB1/US3 | Security Team | Implement Capsule Preview | So that the Security Team can benefit from capsule preview | 3 | Security Team | 2025-10-29 | Compliance
1 | SB1/US4 | User | Implement Role Management | So that the User can benefit from role management | 3 | User | 2026-01-20 | Deployment
1 | SB1/US5 | Backend Team | Implement Notification System | So that the Backend Team can benefit from notification system | 2 | Backend Team | 2025-10-01 | Testing
1 | SB1/US6 | Guardian | Implement Freemium Model Setup | So that the Guardian can benefit from freemium model setup | 2 | Guardian | 2026-02-21 | Testing
1 | SB1/US7 | DevOps | Implement Encryption Implementation | So that the DevOps can benefit from encryption implementation | 1 | DevOps | 2025-12-30 | Compliance
1 | SB1/US8 | DevOps | Implement Cloud Integration | So that the DevOps can benefit from cloud integration | 1 | DevOps | 2026-01-18 | Compliance
1 | SB1/US9 | User | Implement Freemium Model Setup | So that the User can benefit from freemium model setup | 2 | User | 2025-11-17 | Authentication
1 | SB1/US10 | User | Implement Encryption Implementation | So that the User can benefit from encryption implementation | 2 | User | 2026-01-05 | Deployment
1 | SB1/US11 | Guardian | Implement Voice/Video Support | So that the Guardian can benefit from voice/video support | 2 | Guardian | 2026-02-23 | Testing
1 | SB1/US12 | Security Team | Implement Cloud Integration | So that the Security Team can benefit from cloud integration | 2 | Security Team | 2026-02-25 | Deployment
1 | SB1/US13 | Legal Advisor | Implement Guardian Verification | So that the Legal Advisor can benefit from guardian verification | 1 | Legal Advisor | 2026-02-03 | Testing
1 | SB1/US14 | Backend Team | Implement Freemium Model Setup | So that the Backend Team can benefit from freemium model setup | 3 | Backend Team | 2025-10-02 | Compliance
1 | SB1/US15 | Legal Advisor | Implement Encryption Implementation | So that the Legal Advisor can benefit from encryption implementation | 3 | Legal Advisor | 2025-11-25 | Encryption
1 | SB1/US1 | Legal Advisor | Implement Schedule Delivery | So that the Legal Advisor can benefit from schedule delivery | 2 | Legal Advisor | 2025-12-09 | Storage
1 | SB1/US2 | Frontend Team | Implement Blockchain Hashing | So that the Frontend Team can benefit from blockchain hashing | 3 | Frontend Team | 2026-01-26 | Encryption
1 | SB1/US3 | Backend Team | Implement Voice/Video Support | So that the Backend Team can benefit from voice/video support | 2 | Backend Team | 2025-10-13 | UI/UX
1 | SB1/US4 | Guardian | Implement Biometric Alive Check | So that the Guardian can benefit from biometric alive check | 3 | Guardian | 2025-10-24 | Authentication
1 | SB1/US5 | DevOps | Implement Capsule Preview | So that the DevOps can benefit from capsule preview | 3 | DevOps | 2025-12-21 | Testing
1 | SB1/US6 | Backend Team | Implement Notification System | So that the Backend Team can benefit from notification system | 1 | Backend Team | 2025-10-01 | UI/UX
1 | SB1/US7 | DevOps | Implement Voice/Video Support | So that the DevOps can benefit from voice/video support | 3 | DevOps | 2025-12-07 | Testing
1 | SB1/US8 | Backend Team | Implement Voice/Video Support | So that the Backend Team can benefit from voice/video support | 3 | Backend Team | 2025-10-07 | Compliance
1 | SB1/US9 | DevOps | Implement Guardian Verification | So that the DevOps can benefit from guardian verification | 3 | DevOps | 2025-12-31 | Compliance
1 | SB1/US10 | Guardian | Implement Recipient Management | So that the Guardian can benefit from recipient management | 2 | Guardian | 2025-12-18 | Encryption
1 | SB1/US11 | Legal Advisor | Implement Recipient Management | So that the Legal Advisor can benefit from recipient management | 2 | Legal Advisor | 2026-02-06 | Compliance
1 | SB1/US12 | User | Implement Blockchain Hashing | So that the User can benefit from blockchain hashing | 1 | User | 2025-10-13 | Authentication
1 | SB1/US13 | Admin | Implement Voice/Video Support | So that the Admin can benefit from voice/video support | 2 | Admin | 2025-12-15 | Encryption
1 | SB1/US14 | Admin | Implement Biometric Alive Check | So that the Admin can benefit from biometric alive check | 3 | Admin | 2026-02-11 | UI/UX
1 | SB1/US15 | Legal Advisor | Implement Encryption Implementation | So that the Legal Advisor can benefit from encryption implementation | 3 | Legal Advisor | 2025-11-21 | Storage
1 | SB1/US1 | Backend Team | Implement Legal Compliance | So that the Backend Team can benefit from legal compliance | 2 | Backend Team | 2025-11-26 | Compliance
1 | SB1/US2 | Guardian | Implement Freemium Model Setup | So that the Guardian can benefit from freemium model setup | 3 | Guardian | 2026-01-03 | Compliance
1 | SB1/US3 | Legal Advisor | Implement Data Backup | So that the Legal Advisor can benefit from data backup | 3 | Legal Advisor | 2025-10-25 | Notification
1 | SB1/US4 | User | Implement Encryption Implementation | So that the User can benefit from encryption implementation | 1 | User | 2025-12-15 | Notification
1 | SB1/US5 | Legal Advisor | Implement Premium Subscription Setup | So that the Legal Advisor can benefit from premium subscription setup | 3 | Legal Advisor | 2026-03-06 | Encryption
1 | SB1/US6 | Admin | Implement Cloud Integration | So that the Admin can benefit from cloud integration | 1 | Admin | 2025-10-25 | Notification
1 | SB1/US7 | User | Implement Biometric Alive Check | So that the User can benefit from biometric alive check | 2 | User | 2025-10-24 | UI/UX
1 | SB1/US8 | User | Implement User Dashboard | So that the User can benefit from user dashboard | 2 | User | 2026-02-05 | UI/UX
1 | SB1/US9 | Frontend Team | Implement Biometric Alive Check | So that the Frontend Team can benefit from biometric alive check | 3 | Frontend Team | 2025-09-20 | Storage
1 | SB1/US10 | Frontend Team | Implement Schedule Delivery | So that the Frontend Team can benefit from schedule delivery | 2 | Frontend Team | 2025-12-28 | UI/UX
1 | SB1/US11 | Guardian | Implement User Dashboard | So that the Guardian can benefit from user dashboard | 2 | Guardian | 2025-11-28 | Authentication
1 | SB1/US12 | Frontend Team | Implement Freemium Model Setup | So that the Frontend Team can benefit from freemium model setup | 2 | Frontend Team | 2025-11-12 | Deployment
1 | SB1/US13 | Guardian | Implement Guardian Verification | So that the Guardian can benefit from guardian verification | 1 | Guardian | 2025-09-25 | Testing
1 | SB1/US14 | Admin | Implement Premium Subscription Setup | So that the Admin can benefit from premium subscription setup | 2 | Admin | 2026-01-07 | Encryption
1 | SB1/US15 | Guardian | Implement Freemium Model Setup | So that the Guardian can benefit from freemium model setup | 1 | Guardian | 2025-10-13 | Encryption
1 | SB1/US1 | Security Team | Implement Cloud Integration | So that the Security Team can benefit from cloud integration | 2 | Security Team | 2025-10-05 | Testing
1 | SB1/US2 | Backend Team | Implement Blockchain Hashing | So that the Backend Team can benefit from blockchain hashing | 2 | Backend Team | 2026-02-04 | Testing
1 | SB1/US3 | Security Team | Implement Blockchain Hashing | So that the Security Team can benefit from blockchain hashing | 2 | Security Team | 2025-12-25 | Storage
1 | SB1/US4 | Legal Advisor | Implement Recipient Management | So that the Legal Advisor can benefit from recipient management | 1 | Legal Advisor | 2025-11-11 | Storage
1 | SB1/US5 | DevOps | Implement User Dashboard | So that the DevOps can benefit from user dashboard | 1 | DevOps | 2026-02-22 | Storage
2 | SB2/US6 | Frontend Team | Implement Template Selection | So that the Frontend Team can benefit from template selection | 3 | Frontend Team | 2025-10-29 | Storage
2 | SB2/US7 | Backend Team | Implement Template Selection | So that the Backend Team can benefit from template selection | 2 | Backend Team | 2026-03-03 | Encryption
2 | SB2/US8 | Backend Team | Implement Legal Compliance | So that the Backend Team can benefit from legal compliance | 3 | Backend Team | 2025-10-15 | Storage
2 | SB2/US9 | Frontend Team | Implement Legal Compliance | So that the Frontend Team can benefit from legal compliance | 2 | Frontend Team | 2025-10-11 | Compliance
2 | SB2/US10 | Legal Advisor | Implement Freemium Model Setup | So that the Legal Advisor can benefit from freemium model setup | 1 | Legal Advisor | 2025-11-09 | Authentication
2 | SB2/US11 | Backend Team | Implement Create Capsule | So that the Backend Team can benefit from create capsule | 2 | Backend Team | 2026-03-02 | Deployment
2 | SB2/US12 | Guardian | Implement Capsule Preview | So that the Guardian can benefit from capsule preview | 2 | Guardian | 2026-01-02 | Deployment
2 | SB2/US13 | User | Implement Voice/Video Support | So that the User can benefit from voice/video support | 3 | User | 2025-10-06 | UI/UX
2 | SB2/US14 | Guardian | Implement Capsule Preview | So that the Guardian can benefit from capsule preview | 2 | Guardian | 2026-03-15 | Storage
2 | SB2/US15 | User | Implement Notification System | So that the User can benefit from notification system | 2 | User | 2025-10-26 | Compliance
2 | SB2/US1 | DevOps | Implement Role Management | So that the DevOps can benefit from role management | 3 | DevOps | 2026-03-15 | Encryption
2 | SB2/US2 | Legal Advisor | Implement Data Backup | So that the Legal Advisor can benefit from data backup | 1 | Legal Advisor | 2026-01-20 | Deployment
2 | SB2/US3 | Guardian | Implement Notification System | So that the Guardian can benefit from notification system | 3 | Guardian | 2025-09-29 | Deployment
2 | SB2/US4 | Frontend Team | Implement Legal Compliance | So that the Frontend Team can benefit from legal compliance | 2 | Frontend Team | 2025-12-24 | Compliance
2 | SB2/US5 | DevOps | Implement Recipient Management | So that the DevOps can benefit from recipient management | 1 | DevOps | 2026-02-06 | Encryption
2 | SB2/US6 | Admin | Implement Biometric Alive Check | So that the Admin can benefit from biometric alive check | 3 | Admin | 2025-12-19 | Testing
2 | SB2/US7 | Guardian | Implement Create Capsule | So that the Guardian can benefit from create capsule | 3 | Guardian | 2025-10-29 | Testing
2 | SB2/US8 | Frontend Team | Implement Biometric Alive Check | So that the Frontend Team can benefit from biometric alive check | 1 | Frontend Team | 2025-10-30 | UI/UX
2 | SB2/US9 | Admin | Implement Event Triggering | So that the Admin can benefit from event triggering | 3 | Admin | 2025-11-05 | Testing
2 | SB2/US10 | Backend Team | Implement Role Management | So that the Backend Team can benefit from role management | 2 | Backend Team | 2026-01-01 | UI/UX
2 | SB2/US11 | Security Team | Implement Guardian Verification | So that the Security Team can benefit from guardian verification | 1 | Security Team | 2025-09-20 | Deployment
2 | SB2/US12 | Security Team | Implement Blockchain Hashing | So that the Security Team can benefit from blockchain hashing | 1 | Security Team | 2026-01-07 | Notification
2 | SB2/US13 | Admin | Implement Blockchain Hashing | So that the Admin can benefit from blockchain hashing | 3 | Admin | 2025-11-15 | Storage
2 | SB2/US14 | Legal Advisor | Implement Notification System | So that the Legal Advisor can benefit from notification system | 1 | Legal Advisor | 2025-10-25 | Testing
2 | SB2/US15 | User | Implement Role Management | So that the User can benefit from role management | 2 | User | 2025-10-12 | UI/UX
2 | SB2/US1 | Admin | Implement Create Capsule | So that the Admin can benefit from create capsule | 3 | Admin | 2025-10-24 | Deployment
2 | SB2/US2 | User | Implement Role Management | So that the User can benefit from role management | 2 | User | 2025-11-10 | Encryption
2 | SB2/US3 | Admin | Implement Upload Media | So that the Admin can benefit from upload media | 3 | Admin | 2026-02-11 | UI/UX
2 | SB2/US4 | Backend Team | Implement Cloud Integration | So that the Backend Team can benefit from cloud integration | 3 | Backend Team | 2025-12-02 | Compliance
2 | SB2/US5 | User | Implement Create Capsule | So that the User can benefit from create capsule | 3 | User | 2025-09-23 | UI/UX
2 | SB2/US6 | Security Team | Implement Recipient Management | So that the Security Team can benefit from recipient management | 3 | Security Team | 2025-11-09 | UI/UX
2 | SB2/US7 | Security Team | Implement Capsule Preview | So that the Security Team can benefit from capsule preview | 1 | Security Team | 2025-12-16 | Deployment
2 | SB2/US8 | Backend Team | Implement Role Management | So that the Backend Team can benefit from role management | 1 | Backend Team | 2025-12-30 | UI/UX
2 | SB2/US9 | Frontend Team | Implement Cloud Integration | So that the Frontend Team can benefit from cloud integration | 2 | Frontend Team | 2026-02-12 | Testing
2 | SB2/US10 | Admin | Implement Guardian Verification | So that the Admin can benefit from guardian verification | 1 | Admin | 2026-01-23 | Authentication
2 | SB2/US11 | DevOps | Implement Role Management | So that the DevOps can benefit from role management | 1 | DevOps | 2025-09-30 | Storage
2 | SB2/US12 | Frontend Team | Implement Role Management | So that the Frontend Team can benefit from role management | 2 | Frontend Team | 2026-01-31 | Encryption
2 | SB2/US13 | User | Implement Upload Media | So that the User can benefit from upload media | 2 | User | 2026-02-04 | UI/UX
2 | SB2/US14 | Legal Advisor | Implement Blockchain Hashing | So that the Legal Advisor can benefit from blockchain hashing | 2 | Legal Advisor | 2025-09-26 | Compliance
2 | SB2/US15 | Legal Advisor | Implement Blockchain Hashing | So that the Legal Advisor can benefit from blockchain hashing | 2 | Legal Advisor | 2025-11-14 | Encryption
2 | SB2/US1 | Frontend Team | Implement Upload Media | So that the Frontend Team can benefit from upload media | 3 | Frontend Team | 2025-10-20 | Notification
2 | SB2/US2 | DevOps | Implement Guardian Verification | So that the DevOps can benefit from guardian verification | 1 | DevOps | 2025-09-24 | UI/UX
2 | SB2/US3 | Guardian | Implement Capsule Preview | So that the Guardian can benefit from capsule preview | 2 | Guardian | 2025-09-28 | Storage
2 | SB2/US4 | Backend Team | Implement Blockchain Hashing | So that the Backend Team can benefit from blockchain hashing | 1 | Backend Team | 2025-12-24 | Compliance
2 | SB2/US5 | Security Team | Implement Create Capsule | So that the Security Team can benefit from create capsule | 2 | Security Team | 2026-03-11 | UI/UX
2 | SB2/US6 | DevOps | Implement Data Backup | So that the DevOps can benefit from data backup | 3 | DevOps | 2025-11-19 | Compliance
2 | SB2/US7 | Legal Advisor | Implement Cloud Integration | So that the Legal Advisor can benefit from cloud integration | 3 | Legal Advisor | 2025-12-04 | Encryption
2 | SB2/US8 | Backend Team | Implement Create Capsule | So that the Backend Team can benefit from create capsule | 3 | Backend Team | 2025-11-28 | Authentication
2 | SB2/US9 | Frontend Team | Implement Capsule Preview | So that the Frontend Team can benefit from capsule preview | 2 | Frontend Team | 2025-10-23 | Compliance
2 | SB2/US10 | Frontend Team | Implement Blockchain Hashing | So that the Frontend Team can benefit from blockchain hashing | 2 | Frontend Team | 2025-11-10 | Deployment
2 | SB2/US11 | Backend Team | Implement Legal Compliance | So that the Backend Team can benefit from legal compliance | 3 | Backend Team | 2026-02-01 | Storage
2 | SB2/US12 | Admin | Implement Upload Media | So that the Admin can benefit from upload media | 2 | Admin | 2026-02-06 | UI/UX
2 | SB2/US13 | Legal Advisor | Implement Premium Subscription Setup | So that the Legal Advisor can benefit from premium subscription setup | 3 | Legal Advisor | 2026-03-13 | UI/UX
2 | SB2/US14 | Backend Team | Implement Encryption Implementation | So that the Backend Team can benefit from encryption implementation | 3 | Backend Team | 2026-01-25 | Encryption
2 | SB2/US15 | DevOps | Implement Voice/Video Support | So that the DevOps can benefit from voice/video support | 2 | DevOps | 2025-11-21 | Testing
2 | SB2/US1 | Security Team | Implement Biometric Alive Check | So that the Security Team can benefit from biometric alive check | 3 | Security Team | 2026-02-13 | UI/UX
2 | SB2/US2 | Guardian | Implement Data Backup | So that the Guardian can benefit from data backup | 2 | Guardian | 2025-12-14 | Notification
2 | SB2/US3 | Backend Team | Implement Notification System | So that the Backend Team can benefit from notification system | 1 | Backend Team | 2025-11-20 | Authentication
2 | SB2/US4 | Backend Team | Implement Event Triggering | So that the Backend Team can benefit from event triggering | 2 | Backend Team | 2026-02-03 | Compliance
2 | SB2/US5 | DevOps | Implement Create Capsule | So that the DevOps can benefit from create capsule | 3 | DevOps | 2026-02-21 | Notification
2 | SB2/US6 | User | Implement Voice/Video Support | So that the User can benefit from voice/video support | 1 | User | 2025-11-07 | Authentication
2 | SB2/US7 | Security Team | Implement Capsule Preview | So that the Security Team can benefit from capsule preview | 3 | Security Team | 2025-10-31 | UI/UX
2 | SB2/US8 | Admin | Implement Data Backup | So that the Admin can benefit from data backup | 2 | Admin | 2025-11-01 | Deployment
2 | SB2/US9 | User | Implement Schedule Delivery | So that the User can benefit from schedule delivery | 1 | User | 2025-11-26 | UI/UX
2 | SB2/US10 | Admin | Implement Biometric Alive Check | So that the Admin can benefit from biometric alive check | 1 | Admin | 2025-12-24 | Deployment
3 | SB3/US11 | Frontend Team | Implement Data Backup | So that the Frontend Team can benefit from data backup | 3 | Frontend Team | 2026-02-06 | UI/UX
3 | SB3/US12 | Backend Team | Implement Notification System | So that the Backend Team can benefit from notification system | 1 | Backend Team | 2026-03-12 | Authentication
3 | SB3/US13 | Backend Team | Implement Blockchain Hashing | So that the Backend Team can benefit from blockchain hashing | 2 | Backend Team | 2025-12-02 | Notification
3 | SB3/US14 | Frontend Team | Implement Legal Compliance | So that the Frontend Team can benefit from legal compliance | 2 | Frontend Team | 2026-02-13 | Compliance
3 | SB3/US15 | Security Team | Implement Role Management | So that the Security Team can benefit from role management | 1 | Security Team | 2026-02-15 | Notification
3 | SB3/US1 | Guardian | Implement Upload Media | So that the Guardian can benefit from upload media | 1 | Guardian | 2026-01-26 | Notification
3 | SB3/US2 | Backend Team | Implement Role Management | So that the Backend Team can benefit from role management | 3 | Backend Team | 2026-03-17 | Storage
3 | SB3/US3 | Guardian | Implement Cloud Integration | So that the Guardian can benefit from cloud integration | 3 | Guardian | 2025-10-29 | Encryption
3 | SB3/US4 | Guardian | Implement Biometric Alive Check | So that the Guardian can benefit from biometric alive check | 1 | Guardian | 2026-01-15 | Storage
3 | SB3/US5 | Frontend Team | Implement Biometric Alive Check | So that the Frontend Team can benefit from biometric alive check | 2 | Frontend Team | 2026-01-17 | Compliance
3 | SB3/US6 | Admin | Implement Role Management | So that the Admin can benefit from role management | 1 | Admin | 2025-09-25 | Compliance
3 | SB3/US7 | User | Implement Create Capsule | So that the User can benefit from create capsule | 3 | User | 2025-11-28 | Deployment
3 | SB3/US8 | Guardian | Implement Encryption Implementation | So that the Guardian can benefit from encryption implementation | 2 | Guardian | 2025-12-10 | Storage
3 | SB3/US9 | DevOps | Implement Event Triggering | So that the DevOps can benefit from event triggering | 2 | DevOps | 2026-01-21 | Testing
3 | SB3/US10 | DevOps | Implement Role Management | So that the DevOps can benefit from role management | 3 | DevOps | 2026-01-22 | Storage
3 | SB3/US11 | DevOps | Implement Schedule Delivery | So that the DevOps can benefit from schedule delivery | 3 | DevOps | 2025-12-05 | Compliance
3 | SB3/US12 | Security Team | Implement User Dashboard | So that the Security Team can benefit from user dashboard | 2 | Security Team | 2025-10-20 | Notification
3 | SB3/US13 | Security Team | Implement Capsule Preview | So that the Security Team can benefit from capsule preview | 1 | Security Team | 2025-12-16 | Deployment
3 | SB3/US14 | DevOps | Implement Freemium Model Setup | So that the DevOps can benefit from freemium model setup | 2 | DevOps | 2026-01-04 | UI/UX
3 | SB3/US15 | DevOps | Implement Notification System | So that the DevOps can benefit from notification system | 1 | DevOps | 2025-10-26 | Storage
3 | SB3/US1 | Security Team | Implement Create Capsule | So that the Security Team can benefit from create capsule | 1 | Security Team | 2025-11-18 | Authentication
3 | SB3/US2 | User | Implement Freemium Model Setup | So that the User can benefit from freemium model setup | 2 | User | 2025-10-10 | UI/UX
3 | SB3/US3 | Guardian | Implement Role Management | So that the Guardian can benefit from role management | 2 | Guardian | 2025-12-30 | Compliance
3 | SB3/US4 | User | Implement Event Triggering | So that the User can benefit from event triggering | 1 | User | 2025-10-21 | Testing
3 | SB3/US5 | Admin | Implement Schedule Delivery | So that the Admin can benefit from schedule delivery | 2 | Admin | 2025-09-24 | Notification
3 | SB3/US6 | Admin | Implement Cloud Integration | So that the Admin can benefit from cloud integration | 1 | Admin | 2026-01-09 | Deployment
3 | SB3/US7 | Security Team | Implement Voice/Video Support | So that the Security Team can benefit from voice/video support | 2 | Security Team | 2026-01-03 | Compliance
3 | SB3/US8 | User | Implement Notification System | So that the User can benefit from notification system | 3 | User | 2025-12-10 | Storage
3 | SB3/US9 | DevOps | Implement Create Capsule | So that the DevOps can benefit from create capsule | 2 | DevOps | 2025-11-26 | Testing
3 | SB3/US10 | Legal Advisor | Implement Guardian Verification | So that the Legal Advisor can benefit from guardian verification | 1 | Legal Advisor | 2025-11-02 | UI/UX
3 | SB3/US11 | User | Implement Blockchain Hashing | So that the User can benefit from blockchain hashing | 3 | User | 2026-02-27 | Storage
3 | SB3/US12 | Security Team | Implement Notification System | So that the Security Team can benefit from notification system | 3 | Security Team | 2025-09-21 | Testing
3 | SB3/US13 | Frontend Team | Implement Data Backup | So that the Frontend Team can benefit from data backup | 1 | Frontend Team | 2026-02-28 | UI/UX
3 | SB3/US14 | Frontend Team | Implement Recipient Management | So that the Frontend Team can benefit from recipient management | 1 | Frontend Team | 2026-01-18 | UI/UX
3 | SB3/US15 | Security Team | Implement Capsule Preview | So that the Security Team can benefit from capsule preview | 3 | Security Team | 2025-11-01 | Notification
3 | SB3/US1 | Guardian | Implement Legal Compliance | So that the Guardian can benefit from legal compliance | 3 | Guardian | 2026-01-28 | Deployment
3 | SB3/US2 | Guardian | Implement User Dashboard | So that the Guardian can benefit from user dashboard | 2 | Guardian | 2025-11-30 | UI/UX
3 | SB3/US3 | Frontend Team | Implement Premium Subscription Setup | So that the Frontend Team can benefit from premium subscription setup | 1 | Frontend Team | 2025-10-13 | UI/UX
3 | SB3/US4 | Backend Team | Implement Cloud Integration | So that the Backend Team can benefit from cloud integration | 1 | Backend Team | 2026-03-04 | Deployment
3 | SB3/US5 | Backend Team | Implement Legal Compliance | So that the Backend Team can benefit from legal compliance | 3 | Backend Team | 2026-02-18 | UI/UX
3 | SB3/US6 | Frontend Team | Implement Notification System | So that the Frontend Team can benefit from notification system | 2 | Frontend Team | 2026-01-22 | Compliance
3 | SB3/US7 | Guardian | Implement Data Backup | So that the Guardian can benefit from data backup | 2 | Guardian | 2025-11-12 | Notification
3 | SB3/US8 | Admin | Implement Upload Media | So that the Admin can benefit from upload media | 2 | Admin | 2026-02-23 | Authentication
3 | SB3/US9 | Admin | Implement User Dashboard | So that the Admin can benefit from user dashboard | 1 | Admin | 2026-01-10 | Notification
3 | SB3/US10 | Security Team | Implement User Dashboard | So that the Security Team can benefit from user dashboard | 2 | Security Team | 2025-09-30 | Testing
3 | SB3/US11 | Backend Team | Implement Schedule Delivery | So that the Backend Team can benefit from schedule delivery | 2 | Backend Team | 2025-09-24 | Storage
3 | SB3/US12 | Legal Advisor | Implement Notification System | So that the Legal Advisor can benefit from notification system | 1 | Legal Advisor | 2026-02-04 | Testing
3 | SB3/US13 | DevOps | Implement Data Backup | So that the DevOps can benefit from data backup | 1 | DevOps | 2025-11-06 | Authentication
3 | SB3/US14 | Security Team | Implement Blockchain Hashing | So that the Security Team can benefit from blockchain hashing | 1 | Security Team | 2025-11-02 | Encryption
3 | SB3/US15 | Frontend Team | Implement Event Triggering | So that the Frontend Team can benefit from event triggering | 3 | Frontend Team | 2025-10-10 | UI/UX
3 | SB3/US1 | Guardian | Implement Biometric Alive Check | So that the Guardian can benefit from biometric alive check | 2 | Guardian | 2025-12-10 | Storage
3 | SB3/US2 | Legal Advisor | Implement Capsule Preview | So that the Legal Advisor can benefit from capsule preview | 1 | Legal Advisor | 2025-12-29 | Storage
3 | SB3/US3 | Admin | Implement Capsule Preview | So that the Admin can benefit from capsule preview | 3 | Admin | 2025-11-15 | Authentication
3 | SB3/US4 | User | Implement Event Triggering | So that the User can benefit from event triggering | 3 | User | 2025-11-19 | Notification
3 | SB3/US5 | Legal Advisor | Implement Capsule Preview | So that the Legal Advisor can benefit from capsule preview | 2 | Legal Advisor | 2025-11-24 | UI/UX
3 | SB3/US6 | Legal Advisor | Implement User Dashboard | So that the Legal Advisor can benefit from user dashboard | 1 | Legal Advisor | 2025-11-28 | Storage
3 | SB3/US7 | Security Team | Implement Cloud Integration | So that the Security Team can benefit from cloud integration | 1 | Security Team | 2026-03-10 | Encryption
3 | SB3/US8 | Security Team | Implement Schedule Delivery | So that the Security Team can benefit from schedule delivery | 1 | Security Team | 2026-01-30 | Storage
3 | SB3/US9 | Admin | Implement User Dashboard | So that the Admin can benefit from user dashboard | 3 | Admin | 2025-11-29 | Compliance
3 | SB3/US10 | Admin | Implement Create Capsule | So that the Admin can benefit from create capsule | 1 | Admin | 2026-01-26 | Testing
3 | SB3/US11 | Admin | Implement Schedule Delivery | So that the Admin can benefit from schedule delivery | 2 | Admin | 2025-10-08 | Notification
3 | SB3/US12 | Guardian | Implement Biometric Alive Check | So that the Guardian can benefit from biometric alive check | 2 | Guardian | 2026-01-03 | Notification
3 | SB3/US13 | Admin | Implement Capsule Preview | So that the Admin can benefit from capsule preview | 3 | Admin | 2026-02-07 | Encryption
3 | SB3/US14 | Backend Team | Implement Template Selection | So that the Backend Team can benefit from template selection | 1 | Backend Team | 2025-12-04 | Compliance
3 | SB3/US15 | Admin | Implement Notification System | So that the Admin can benefit from notification system | 1 | Admin | 2026-01-17 | UI/UX
4 | SB4/US1 | Security Team | Implement Cloud Integration | So that the Security Team can benefit from cloud integration | 2 | Security Team | 2025-10-05 | Deployment
4 | SB4/US2 | Backend Team | Implement Notification System | So that the Backend Team can benefit from notification system | 1 | Backend Team | 2026-03-17 | Encryption
4 | SB4/US3 | Frontend Team | Implement Blockchain Hashing | So that the Frontend Team can benefit from blockchain hashing | 2 | Frontend Team | 2026-02-12 | Testing
4 | SB4/US4 | Guardian | Implement Guardian Verification | So that the Guardian can benefit from guardian verification | 1 | Guardian | 2025-12-12 | Notification
4 | SB4/US5 | Security Team | Implement Create Capsule | So that the Security Team can benefit from create capsule | 2 | Security Team | 2026-03-14 | Encryption
4 | SB4/US6 | Legal Advisor | Implement Data Backup | So that the Legal Advisor can benefit from data backup | 1 | Legal Advisor | 2026-01-29 | Testing
4 | SB4/US7 | Frontend Team | Implement Schedule Delivery | So that the Frontend Team can benefit from schedule delivery | 3 | Frontend Team | 2025-09-23 | Testing
4 | SB4/US8 | Guardian | Implement Schedule Delivery | So that the Guardian can benefit from schedule delivery | 1 | Guardian | 2026-02-03 | Notification
4 | SB4/US9 | Frontend Team | Implement Legal Compliance | So that the Frontend Team can benefit from legal compliance | 1 | Frontend Team | 2025-11-08 | Notification
4 | SB4/US10 | Legal Advisor | Implement Cloud Integration | So that the Legal Advisor can benefit from cloud integration | 3 | Legal Advisor | 2026-01-28 | Encryption
4 | SB4/US11 | User | Implement Create Capsule | So that the User can benefit from create capsule | 3 | User | 2025-11-19 | Compliance
4 | SB4/US12 | Security Team | Implement Capsule Preview | So that the Security Team can benefit from capsule preview | 3 | Security Team | 2025-11-11 | UI/UX
4 | SB4/US13 | Legal Advisor | Implement Upload Media | So that the Legal Advisor can benefit from upload media | 2 | Legal Advisor | 2025-10-15 | Compliance
4 | SB4/US14 | User | Implement Blockchain Hashing | So that the User can benefit from blockchain hashing | 2 | User | 2025-11-26 | Testing
4 | SB4/US15 | User | Implement Cloud Integration | So that the User can benefit from cloud integration | 1 | User | 2026-01-21 | Testing
4 | SB4/US1 | Legal Advisor | Implement Recipient Management | So that the Legal Advisor can benefit from recipient management | 3 | Legal Advisor | 2026-03-09 | Encryption
4 | SB4/US2 | Guardian | Implement Capsule Preview | So that the Guardian can benefit from capsule preview | 1 | Guardian | 2026-03-04 | UI/UX
4 | SB4/US3 | Guardian | Implement Recipient Management | So that the Guardian can benefit from recipient management | 3 | Guardian | 2025-09-25 | Authentication
4 | SB4/US4 | Legal Advisor | Implement Encryption Implementation | So that the Legal Advisor can benefit from encryption implementation | 2 | Legal Advisor | 2026-02-08 | Notification
4 | SB4/US5 | Guardian | Implement Role Management | So that the Guardian can benefit from role management | 2 | Guardian | 2026-01-26 | Testing
4 | SB4/US6 | Frontend Team | Implement Legal Compliance | So that the Frontend Team can benefit from legal compliance | 3 | Frontend Team | 2026-01-30 | Storage
4 | SB4/US7 | Guardian | Implement Event Triggering | So that the Guardian can benefit from event triggering | 1 | Guardian | 2026-02-22 | Deployment
4 | SB4/US8 | Guardian | Implement Create Capsule | So that the Guardian can benefit from create capsule | 2 | Guardian | 2026-01-06 | Authentication
4 | SB4/US9 | DevOps | Implement Guardian Verification | So that the DevOps can benefit from guardian verification | 1 | DevOps | 2025-10-21 | Encryption
4 | SB4/US10 | Guardian | Implement User Dashboard | So that the Guardian can benefit from user dashboard | 2 | Guardian | 2026-03-08 | Testing
4 | SB4/US11 | Frontend Team | Implement User Dashboard | So that the Frontend Team can benefit from user dashboard | 3 | Frontend Team | 2025-11-26 | UI/UX
4 | SB4/US12 | Admin | Implement Role Management | So that the Admin can benefit from role management | 1 | Admin | 2025-11-08 | Compliance
4 | SB4/US13 | Frontend Team | Implement Encryption Implementation | So that the Frontend Team can benefit from encryption implementation | 3 | Frontend Team | 2026-01-27 | Compliance
4 | SB4/US14 | DevOps | Implement Create Capsule | So that the DevOps can benefit from create capsule | 1 | DevOps | 2026-02-11 | Notification
4 | SB4/US15 | User | Implement Blockchain Hashing | So that the User can benefit from blockchain hashing | 1 | User | 2025-09-29 | Storage
4 | SB4/US1 | Security Team | Implement Event Triggering | So that the Security Team can benefit from event triggering | 2 | Security Team | 2026-02-11 | Encryption
4 | SB4/US2 | Guardian | Implement Biometric Alive Check | So that the Guardian can benefit from biometric alive check | 1 | Guardian | 2025-10-01 | Authentication
4 | SB4/US3 | Security Team | Implement Freemium Model Setup | So that the Security Team can benefit from freemium model setup | 1 | Security Team | 2026-03-12 | Testing
4 | SB4/US4 | Security Team | Implement Role Management | So that the Security Team can benefit from role management | 3 | Security Team | 2025-11-09 | Compliance
4 | SB4/US5 | DevOps | Implement Schedule Delivery | So that the DevOps can benefit from schedule delivery | 1 | DevOps | 2026-02-11 | Authentication
4 | SB4/US6 | Frontend Team | Implement Data Backup | So that the Frontend Team can benefit from data backup | 3 | Frontend Team | 2026-01-28 | Testing
4 | SB4/US7 | Backend Team | Implement Upload Media | So that the Backend Team can benefit from upload media | 2 | Backend Team | 2025-11-18 | Deployment
4 | SB4/US8 | User | Implement Schedule Delivery | So that the User can benefit from schedule delivery | 1 | User | 2026-03-09 | Storage
4 | SB4/US9 | Frontend Team | Implement Upload Media | So that the Frontend Team can benefit from upload media | 1 | Frontend Team | 2025-12-06 | UI/UX
4 | SB4/US10 | Frontend Team | Implement Encryption Implementation | So that the Frontend Team can benefit from encryption implementation | 1 | Frontend Team | 2026-01-12 | Storage
4 | SB4/US11 | User | Implement Legal Compliance | So that the User can benefit from legal compliance | 2 | User | 2025-10-01 | Encryption
4 | SB4/US12 | Legal Advisor | Implement Create Capsule | So that the Legal Advisor can benefit from create capsule | 1 | Legal Advisor | 2026-01-30 | Notification
4 | SB4/US13 | User | Implement Event Triggering | So that the User can benefit from event triggering | 3 | User | 2025-12-09 | Authentication
4 | SB4/US14 | Guardian | Implement Event Triggering | So that the Guardian can benefit from event triggering | 1 | Guardian | 2025-11-05 | Authentication
4 | SB4/US15 | User | Implement Cloud Integration | So that the User can benefit from cloud integration | 3 | User | 2026-02-13 | Encryption
4 | SB4/US1 | Legal Advisor | Implement Recipient Management | So that the Legal Advisor can benefit from recipient management | 3 | Legal Advisor | 2025-10-08 | Deployment
4 | SB4/US2 | Legal Advisor | Implement Create Capsule | So that the Legal Advisor can benefit from create capsule | 3 | Legal Advisor | 2026-03-16 | Storage
4 | SB4/US3 | Guardian | Implement Schedule Delivery | So that the Guardian can benefit from schedule delivery | 3 | Guardian | 2026-02-03 | Deployment
4 | SB4/US4 | DevOps | Implement Role Management | So that the DevOps can benefit from role management | 2 | DevOps | 2025-12-06 | Compliance
4 | SB4/US5 | Admin | Implement Template Selection | So that the Admin can benefit from template selection | 1 | Admin | 2025-09-28 | Compliance
4 | SB4/US6 | DevOps | Implement Freemium Model Setup | So that the DevOps can benefit from freemium model setup | 2 | DevOps | 2026-01-14 | Storage
4 | SB4/US7 | Admin | Implement Recipient Management | So that the Admin can benefit from recipient management | 1 | Admin | 2025-11-02 | UI/UX
4 | SB4/US8 | Frontend Team | Implement Capsule Preview | So that the Frontend Team can benefit from capsule preview | 2 | Frontend Team | 2025-12-04 | UI/UX
4 | SB4/US9 | Backend Team | Implement Schedule Delivery | So that the Backend Team can benefit from schedule delivery | 1 | Backend Team | 2026-01-04 | Compliance
4 | SB4/US10 | Admin | Implement Freemium Model Setup | So that the Admin can benefit from freemium model setup | 2 | Admin | 2026-02-08 | Storage
4 | SB4/US11 | DevOps | Implement Premium Subscription Setup | So that the DevOps can benefit from premium subscription setup | 3 | DevOps | 2026-02-07 | Compliance
4 | SB4/US12 | Guardian | Implement Event Triggering | So that the Guardian can benefit from event triggering | 3 | Guardian | 2025-10-18 | Storage
4 | SB4/US13 | Guardian | Implement Premium Subscription Setup | So that the Guardian can benefit from premium subscription setup | 1 | Guardian | 2026-02-10 | Compliance
4 | SB4/US14 | Admin | Implement Legal Compliance | So that the Admin can benefit from legal compliance | 1 | Admin | 2025-09-23 | Storage
4 | SB4/US15 | Security Team | Implement Freemium Model Setup | So that the Security Team can benefit from freemium model setup | 2 | Security Team | 2025-12-21 | Deployment
4 | SB4/US1 | Backend Team | Implement Premium Subscription Setup | So that the Backend Team can benefit from premium subscription setup | 2 | Backend Team | 2025-11-02 | Testing
4 | SB4/US2 | Frontend Team | Implement Recipient Management | So that the Frontend Team can benefit from recipient management | 1 | Frontend Team | 2025-10-18 | Compliance
4 | SB4/US3 | Admin | Implement Cloud Integration | So that the Admin can benefit from cloud integration | 3 | Admin | 2026-02-19 | Storage
4 | SB4/US4 | Security Team | Implement Capsule Preview | So that the Security Team can benefit from capsule preview | 1 | Security Team | 2025-11-01 | Storage
4 | SB4/US5 | Admin | Implement Cloud Integration | So that the Admin can benefit from cloud integration | 3 | Admin | 2026-03-09 | Authentication

## sprint 1
SPRINT BACKLOG 1
US ID | USER STORY | TASK ID | TASKS | TM | STATUS (NOT STARTED / IN PROGRESS / COMPLETED) | ESTIMATED DATE OF TASK COMPLETION
SPRINT 1 - <Digital College>
SB1/US1 | Implement Guardian Verification | SB1/US1/T1 | Design frontend/backend components for implement guardian verification | rishank jain | Not Started | 2025-09-10
SB1/US1 | Implement Guardian Verification | SB1/US1/T2 | Develop API and integrate database for implement guardian verification | rishank jain | Not Started | 2025-09-10
SB1/US1 | Implement Guardian Verification | SB1/US1/T3 | Test and validate functionality of implement guardian verification | rishank jain | Not Started | 2025-09-11
SB1/US2 | Implement Schedule Delivery | SB1/US2/T1 | Design frontend/backend components for implement schedule delivery | aayush pareek | Not Started | 2025-09-11
SB1/US2 | Implement Schedule Delivery | SB1/US2/T2 | Develop API and integrate database for implement schedule delivery | aayush pareek | Not Started | 2025-09-10
SB1/US2 | Implement Schedule Delivery | SB1/US2/T3 | Test and validate functionality of implement schedule delivery | aayush pareek | Not Started | 2025-09-11
SB1/US3 | Implement Encryption Implementation | SB1/US3/T1 | Design frontend/backend components for implement encryption implementation | dev choudhary | Not Started | 2025-09-11
SB1/US3 | Implement Encryption Implementation | SB1/US3/T2 | Develop API and integrate database for implement encryption implementation | dev choudhary | Not Started | 2025-09-12
SB1/US3 | Implement Encryption Implementation | SB1/US3/T3 | Test and validate functionality of implement encryption implementation | dev choudhary | Not Started | 2025-09-12
SB1/US4 | Implement Upload Media | SB1/US4/T1 | Design frontend/backend components for implement upload media | rishank jain | Not Started | 2025-09-12
SB1/US4 | Implement Upload Media | SB1/US4/T2 | Develop API and integrate database for implement upload media | rishank jain | Not Started | 2025-09-15
SB1/US4 | Implement Upload Media | SB1/US4/T3 | Test and validate functionality of implement upload media | rishank jain | Not Started | 2025-09-15
SB1/US5 | Implement Create Capsule | SB1/US5/T1 | Design frontend/backend components for implement create capsule | aayush pareek | Not Started | 2025-09-15
SB1/US5 | Implement Create Capsule | SB1/US5/T2 | Develop API and integrate database for implement create capsule | aayush pareek | Not Started | 2025-09-16
SB1/US5 | Implement Create Capsule | SB1/US5/T3 | Test and validate functionality of implement create capsule | aayush pareek | Not Started | 2025-09-16
SB1/US6 | Implement Biometric Alive Check | SB1/US6/T1 | Design frontend/backend components for implement biometric alive check | dev choudhary | Not Started | 2025-09-17
SB1/US6 | Implement Biometric Alive Check | SB1/US6/T2 | Develop API and integrate database for implement biometric alive check | dev choudhary | Not Started | 2025-09-16
SB1/US6 | Implement Biometric Alive Check | SB1/US6/T3 | Test and validate functionality of implement biometric alive check | dev choudhary | Not Started | 2025-09-17
SB1/US7 | Implement Cloud Integration | SB1/US7/T1 | Design frontend/backend components for implement cloud integration | rishank jain | Not Started | 2025-09-17
SB1/US7 | Implement Cloud Integration | SB1/US7/T2 | Develop API and integrate database for implement cloud integration | rishank jain | Not Started | 2025-09-18
SB1/US7 | Implement Cloud Integration | SB1/US7/T3 | Test and validate functionality of implement cloud integration | rishank jain | Not Started | 2025-09-18
SB1/US8 | Implement Premium Subscription Setup | SB1/US8/T1 | Design frontend/backend components for implement premium subscription setup | aayush pareek | Not Started | 2025-09-19
SB1/US8 | Implement Premium Subscription Setup | SB1/US8/T2 | Develop API and integrate database for implement premium subscription setup | aayush pareek | Not Started | 2025-09-22
SB1/US8 | Implement Premium Subscription Setup | SB1/US8/T3 | Test and validate functionality of implement premium subscription setup | aayush pareek | Not Started | 2025-09-22
SB1/US9 | Implement Create Capsule | SB1/US9/T1 | Design frontend/backend components for implement create capsule | dev choudhary | Not Started | 2025-09-12
SB1/US9 | Implement Create Capsule | SB1/US9/T2 | Develop API and integrate database for implement create capsule | dev choudhary | Not Started | 2025-09-15
SB1/US9 | Implement Create Capsule | SB1/US9/T3 | Test and validate functionality of implement create capsule | dev choudhary | Not Started | 2025-09-16
SB1/US10 | Implement Voice/Video Support | SB1/US10/T1 | Design frontend/backend components for implement voice/video support | rishank jain | Not Started | 2025-09-16
SB1/US10 | Implement Voice/Video Support | SB1/US10/T2 | Develop API and integrate database for implement voice/video support | rishank jain | Not Started | 2025-09-23
SB1/US10 | Implement Voice/Video Support | SB1/US10/T3 | Test and validate functionality of implement voice/video support | rishank jain | Not Started | 2025-09-24
SB1/US11 | Implement User Dashboard | SB1/US11/T1 | Design frontend/backend components for implement user dashboard | aayush pareek | Not Started | 2025-09-24
SB1/US11 | Implement User Dashboard | SB1/US11/T2 | Develop API and integrate database for implement user dashboard | aayush pareek | Not Started | 2025-09-25
SB1/US11 | Implement User Dashboard | SB1/US11/T3 | Test and validate functionality of implement user dashboard | aayush pareek | Not Started | 2025-09-25
SB1/US12 | Implement Create Capsule | SB1/US12/T1 | Design frontend/backend components for implement create capsule | dev choudhary | Not Started | 2025-09-26
SB1/US12 | Implement Create Capsule | SB1/US12/T2 | Develop API and integrate database for implement create capsule | dev choudhary | Not Started | 2025-09-26
SB1/US12 | Implement Create Capsule | SB1/US12/T3 | Test and validate functionality of implement create capsule | dev choudhary | Not Started | 2025-09-29
SB1/US13 | Implement Role Management | SB1/US13/T1 | Design frontend/backend components for implement role management | rishank jain | Not Started | 2025-09-23
SB1/US13 | Implement Role Management | SB1/US13/T2 | Develop API and integrate database for implement role management | rishank jain | Not Started | 2025-09-24
SB1/US13 | Implement Role Management | SB1/US13/T3 | Test and validate functionality of implement role management | rishank jain | Not Started | 2025-09-25
SB1/US14 | Implement Upload Media | SB1/US14/T1 | Design frontend/backend components for implement upload media | aayush pareek | Not Started | 2025-09-25
SB1/US14 | Implement Upload Media | SB1/US14/T2 | Develop API and integrate database for implement upload media | aayush pareek | Not Started | 2025-09-29
SB1/US14 | Implement Upload Media | SB1/US14/T3 | Test and validate functionality of implement upload media | aayush pareek | Not Started | 2025-09-30
SB1/US15 | Implement Premium Subscription Setup | SB1/US15/T1 | Design frontend/backend components for implement premium subscription setup | dev choudhary | Not Started | 2025-09-30
SB1/US15 | Implement Premium Subscription Setup | SB1/US15/T2 | Develop API and integrate database for implement premium subscription setup | dev choudhary | Not Started | 2025-10-01
SB1/US15 | Implement Premium Subscription Setup | SB1/US15/T3 | Test and validate functionality of implement premium subscription setup | dev choudhary | Not Started | 2025-10-02
SB1/US16 | Implement Role Management | SB1/US1/T1 | Design frontend/backend components for implement role management | rishank jain | Not Started | 2025-10-03
SB1/US16 | Implement Role Management | SB1/US1/T2 | Develop API and integrate database for implement role management | rishank jain | Not Started | 2025-10-03
SB1/US16 | Implement Role Management | SB1/US1/T3 | Test and validate functionality of implement role management | rishank jain | Not Started | 2025-10-06
SB1/US17 | Implement Freemium Model Setup | SB1/US2/T1 | Design frontend/backend components for implement freemium model setup | aayush pareek | Not Started | 2025-09-18
SB1/US17 | Implement Freemium Model Setup | SB1/US2/T2 | Develop API and integrate database for implement freemium model setup | aayush pareek | Not Started | 2025-09-19
SB1/US17 | Implement Freemium Model Setup | SB1/US2/T3 | Test and validate functionality of implement freemium model setup | aayush pareek | Not Started | 2025-09-22
SB1/US18 | Implement Capsule Preview | SB1/US3/T1 | Design frontend/backend components for implement capsule preview | dev choudhary | Not Started | 2025-09-22
SB1/US18 | Implement Capsule Preview | SB1/US3/T2 | Develop API and integrate database for implement capsule preview | dev choudhary | Not Started | 2025-10-02
SB1/US18 | Implement Capsule Preview | SB1/US3/T3 | Test and validate functionality of implement capsule preview | dev choudhary | Not Started | 2025-10-03
SB1/US19 | Implement Role Management | SB1/US4/T1 | Design frontend/backend components for implement role management | rishank jain | Not Started | 2025-10-06
SB1/US19 | Implement Role Management | SB1/US4/T2 | Develop API and integrate database for implement role management | rishank jain | Not Started | 2025-10-06
SB1/US19 | Implement Role Management | SB1/US4/T3 | Test and validate functionality of implement role management | rishank jain | Not Started | 2025-09-29
SB1/US20 | Implement Notification System | SB1/US5/T1 | Design frontend/backend components for implement notification system | aayush pareek | Not Started | 2025-09-30
SB1/US20 | Implement Notification System | SB1/US5/T2 | Develop API and integrate database for implement notification system | aayush pareek | Not Started | 2025-10-01
SB1/US20 | Implement Notification System | SB1/US5/T3 | Test and validate functionality of implement notification system | aayush pareek | Not Started | 2025-10-02
SB1/US21 | Implement Freemium Model Setup | SB1/US6/T1 | Design frontend/backend components for implement freemium model setup | dev choudhary | Not Started | 2025-10-07
SB1/US21 | Implement Freemium Model Setup | SB1/US6/T2 | Develop API and integrate database for implement freemium model setup | dev choudhary | Not Started | 2025-10-08
SB1/US21 | Implement Freemium Model Setup | SB1/US6/T3 | Test and validate functionality of implement freemium model setup | dev choudhary | Not Started | 2025-10-08
SB1/US22 | Implement Encryption Implementation | SB1/US7/T1 | Design frontend/backend components for implement encryption implementation | rishank jain | Not Started | 2025-10-09
SB1/US22 | Implement Encryption Implementation | SB1/US7/T2 | Develop API and integrate database for implement encryption implementation | rishank jain | Not Started | 2025-09-17
SB1/US22 | Implement Encryption Implementation | SB1/US7/T3 | Test and validate functionality of implement encryption implementation | rishank jain | Not Started | 2025-09-18
SB1/US23 | Implement Cloud Integration | SB1/US8/T1 | Design frontend/backend components for implement cloud integration | aayush pareek | Not Started | 2025-09-18
SB1/US23 | Implement Cloud Integration | SB1/US8/T2 | Develop API and integrate database for implement cloud integration | aayush pareek | Not Started | 2025-09-19
SB1/US23 | Implement Cloud Integration | SB1/US8/T3 | Test and validate functionality of implement cloud integration | aayush pareek | Not Started | 2025-09-17
SB1/US24 | Implement Freemium Model Setup | SB1/US9/T1 | Design frontend/backend components for implement freemium model setup | dev choudhary | Not Started | 2025-09-18
SB1/US24 | Implement Freemium Model Setup | SB1/US9/T2 | Develop API and integrate database for implement freemium model setup | dev choudhary | Not Started | 2025-09-19
SB1/US24 | Implement Freemium Model Setup | SB1/US9/T3 | Test and validate functionality of implement freemium model setup | dev choudhary | Not Started | 2025-09-19
SB1/US25 | Implement Encryption Implementation | SB1/US10/T1 | Design frontend/backend components for implement encryption implementation | rishank jain | Not Started | 2025-10-01
SB1/US25 | Implement Encryption Implementation | SB1/US10/T2 | Develop API and integrate database for implement encryption implementation | rishank jain | Not Started | 2025-10-02
SB1/US25 | Implement Encryption Implementation | SB1/US10/T3 | Test and validate functionality of implement encryption implementation | rishank jain | Not Started | 2025-10-02
SB1/US26 | Implement Voice/Video Support | SB1/US11/T1 | Design frontend/backend components for implement voice/video support | aayush pareek | Not Started | 2025-10-03
SB1/US26 | Implement Voice/Video Support | SB1/US11/T2 | Develop API and integrate database for implement voice/video support | aayush pareek | Not Started | 2025-10-06
SB1/US26 | Implement Voice/Video Support | SB1/US11/T3 | Test and validate functionality of implement voice/video support | aayush pareek | Not Started | 2025-10-07
SB1/US27 | Implement Cloud Integration | SB1/US12/T1 | Design frontend/backend components for implement cloud integration | dev choudhary | Not Started | 2025-10-07
SB1/US27 | Implement Cloud Integration | SB1/US12/T2 | Develop API and integrate database for implement cloud integration | dev choudhary | Not Started | 2025-10-08
SB1/US27 | Implement Cloud Integration | SB1/US12/T3 | Test and validate functionality of implement cloud integration | dev choudhary | Not Started | 2025-10-07
SB1/US28 | Implement Guardian Verification | SB1/US13/T1 | Design frontend/backend components for implement guardian verification | rishank jain | Not Started | 2025-10-08
SB1/US28 | Implement Guardian Verification | SB1/US13/T2 | Develop API and integrate database for implement guardian verification | rishank jain | Not Started | 2025-10-08
SB1/US28 | Implement Guardian Verification | SB1/US13/T3 | Test and validate functionality of implement guardian verification | rishank jain | Not Started | 2025-10-09
SB1/US29 | Implement Freemium Model Setup | SB1/US14/T1 | Design frontend/backend components for implement freemium model setup | aayush pareek | Not Started | 2025-09-23
SB1/US29 | Implement Freemium Model Setup | SB1/US14/T2 | Develop API and integrate database for implement freemium model setup | aayush pareek | Not Started | 2025-09-24
SB1/US29 | Implement Freemium Model Setup | SB1/US14/T3 | Test and validate functionality of implement freemium model setup | aayush pareek | Not Started | 2025-09-24
SB1/US30 | Implement Encryption Implementation | SB1/US15/T1 | Design frontend/backend components for implement encryption implementation | dev choudhary | Not Started | 2025-09-25
SB1/US30 | Implement Encryption Implementation | SB1/US15/T2 | Develop API and integrate database for implement encryption implementation | dev choudhary | Not Started | 2025-09-12
SB1/US30 | Implement Encryption Implementation | SB1/US15/T3 | Test and validate functionality of implement encryption implementation | dev choudhary | Not Started | 2025-09-15
SB1/US31 | Implement Schedule Delivery | SB1/US1/T1 | Design frontend/backend components for implement schedule delivery | rishank jain | Not Started | 2025-09-15
SB1/US31 | Implement Schedule Delivery | SB1/US1/T2 | Develop API and integrate database for implement schedule delivery | rishank jain | Not Started | 2025-09-16
SB1/US31 | Implement Schedule Delivery | SB1/US1/T3 | Test and validate functionality of implement schedule delivery | rishank jain | Not Started | 2025-09-26
SB1/US32 | Implement Blockchain Hashing | SB1/US2/T1 | Design frontend/backend components for implement blockchain hashing | aayush pareek | Not Started | 2025-09-29
SB1/US32 | Implement Blockchain Hashing | SB1/US2/T2 | Develop API and integrate database for implement blockchain hashing | aayush pareek | Not Started | 2025-09-29
SB1/US32 | Implement Blockchain Hashing | SB1/US2/T3 | Test and validate functionality of implement blockchain hashing | aayush pareek | Not Started | 2025-09-30
SB1/US33 | Implement Voice/Video Support | SB1/US3/T1 | Design frontend/backend components for implement voice/video support | dev choudhary | Not Started | 2025-10-01
SB1/US33 | Implement Voice/Video Support | SB1/US3/T2 | Develop API and integrate database for implement voice/video support | dev choudhary | Not Started | 2025-10-02
SB1/US33 | Implement Voice/Video Support | SB1/US3/T3 | Test and validate functionality of implement voice/video support | dev choudhary | Not Started | 2025-10-02
SB1/US34 | Implement Biometric Alive Check | SB1/US4/T1 | Design frontend/backend components for implement biometric alive check | rishank jain | Not Started | 2025-10-03
SB1/US34 | Implement Biometric Alive Check | SB1/US4/T2 | Develop API and integrate database for implement biometric alive check | rishank jain | Not Started | 2025-09-12
SB1/US34 | Implement Biometric Alive Check | SB1/US4/T3 | Test and validate functionality of implement biometric alive check | rishank jain | Not Started | 2025-09-15
SB1/US35 | Implement Capsule Preview | SB1/US5/T1 | Design frontend/backend components for implement capsule preview | aayush pareek | Not Started | 2025-09-15
SB1/US35 | Implement Capsule Preview | SB1/US5/T2 | Develop API and integrate database for implement capsule preview | aayush pareek | Not Started | 2025-09-16
SB1/US35 | Implement Capsule Preview | SB1/US5/T3 | Test and validate functionality of implement capsule preview | aayush pareek | Not Started | 2025-10-07
SB1/US36 | Implement Notification System | SB1/US6/T1 | Design frontend/backend components for implement notification system | dev choudhary | Not Started | 2025-10-08
SB1/US36 | Implement Notification System | SB1/US6/T2 | Develop API and integrate database for implement notification system | dev choudhary | Not Started | 2025-10-08
SB1/US36 | Implement Notification System | SB1/US6/T3 | Test and validate functionality of implement notification system | dev choudhary | Not Started | 2025-10-09
SB1/US37 | Implement Voice/Video Support | SB1/US7/T1 | Design frontend/backend components for implement voice/video support | rishank jain | Not Started | 2025-10-02
SB1/US37 | Implement Voice/Video Support | SB1/US7/T2 | Develop API and integrate database for implement voice/video support | rishank jain | Not Started | 2025-10-03
SB1/US37 | Implement Voice/Video Support | SB1/US7/T3 | Test and validate functionality of implement voice/video support | rishank jain | Not Started | 2025-10-03
SB1/US38 | Implement Voice/Video Support | SB1/US8/T1 | Design frontend/backend components for implement voice/video support | aayush pareek | Not Started | 2025-10-06
SB1/US38 | Implement Voice/Video Support | SB1/US8/T2 | Develop API and integrate database for implement voice/video support | aayush pareek | Not Started | 2025-09-17
SB1/US38 | Implement Voice/Video Support | SB1/US8/T3 | Test and validate functionality of implement voice/video support | aayush pareek | Not Started | 2025-09-18
SB1/US39 | Implement Guardian Verification | SB1/US9/T1 | Design frontend/backend components for implement guardian verification | dev choudhary | Not Started | 2025-09-18
SB1/US39 | Implement Guardian Verification | SB1/US9/T2 | Develop API and integrate database for implement guardian verification | dev choudhary | Not Started | 2025-09-19
SB1/US39 | Implement Guardian Verification | SB1/US9/T3 | Test and validate functionality of implement guardian verification | dev choudhary | Not Started | 2025-09-19
SB1/US40 | Implement Recipient Management | SB1/US10/T1 | Design frontend/backend components for implement recipient management | rishank jain | Not Started | 2025-09-22
SB1/US40 | Implement Recipient Management | SB1/US10/T2 | Develop API and integrate database for implement recipient management | rishank jain | Not Started | 2025-09-23
SB1/US40 | Implement Recipient Management | SB1/US10/T3 | Test and validate functionality of implement recipient management | rishank jain | Not Started | 2025-09-23
SB1/US41 | Implement Recipient Management | SB1/US11/T1 | Design frontend/backend components for implement recipient management | aayush pareek | Not Started | 2025-09-23
SB1/US41 | Implement Recipient Management | SB1/US11/T2 | Develop API and integrate database for implement recipient management | aayush pareek | Not Started | 2025-09-24
SB1/US41 | Implement Recipient Management | SB1/US11/T3 | Test and validate functionality of implement recipient management | aayush pareek | Not Started | 2025-09-24
SB1/US42 | Implement Blockchain Hashing | SB1/US12/T1 | Design frontend/backend components for implement blockchain hashing | dev choudhary | Not Started | 2025-09-25
SB1/US42 | Implement Blockchain Hashing | SB1/US12/T2 | Develop API and integrate database for implement blockchain hashing | dev choudhary | Not Started | 2025-09-25
SB1/US42 | Implement Blockchain Hashing | SB1/US12/T3 | Test and validate functionality of implement blockchain hashing | dev choudhary | Not Started | 2025-09-26
SB1/US43 | Implement Voice/Video Support | SB1/US13/T1 | Design frontend/backend components for implement voice/video support | rishank jain | Not Started | 2025-09-29
SB1/US43 | Implement Voice/Video Support | SB1/US13/T2 | Develop API and integrate database for implement voice/video support | rishank jain | Not Started | 2025-09-29
SB1/US43 | Implement Voice/Video Support | SB1/US13/T3 | Test and validate functionality of implement voice/video support | rishank jain | Not Started | 2025-10-06
SB1/US44 | Implement Biometric Alive Check | SB1/US14/T1 | Design frontend/backend components for implement biometric alive check | aayush pareek | Not Started | 2025-10-07
SB1/US44 | Implement Biometric Alive Check | SB1/US14/T2 | Develop API and integrate database for implement biometric alive check | aayush pareek | Not Started | 2025-10-07
SB1/US44 | Implement Biometric Alive Check | SB1/US14/T3 | Test and validate functionality of implement biometric alive check | aayush pareek | Not Started | 2025-10-08
SB1/US45 | Implement Encryption Implementation | SB1/US15/T1 | Design frontend/backend components for implement encryption implementation | dev choudhary | Not Started | 2025-10-09
SB1/US45 | Implement Encryption Implementation | SB1/US15/T2 | Develop API and integrate database for implement encryption implementation | dev choudhary | Not Started | 2025-10-10
SB1/US45 | Implement Encryption Implementation | SB1/US15/T3 | Test and validate functionality of implement encryption implementation | dev choudhary | Not Started | 2025-10-10
SB1/US46 | Implement Legal Compliance | SB1/US1/T1 | Design frontend/backend components for implement legal compliance | rishank jain | Not Started | 2025-10-13
SB1/US46 | Implement Legal Compliance | SB1/US1/T2 | Develop API and integrate database for implement legal compliance | rishank jain | Not Started | 2025-10-09
SB1/US46 | Implement Legal Compliance | SB1/US1/T3 | Test and validate functionality of implement legal compliance | rishank jain | Not Started | 2025-10-10
SB1/US47 | Implement Freemium Model Setup | SB1/US2/T1 | Design frontend/backend components for implement freemium model setup | aayush pareek | Not Started | 2025-10-10
SB1/US47 | Implement Freemium Model Setup | SB1/US2/T2 | Develop API and integrate database for implement freemium model setup | aayush pareek | Not Started | 2025-10-13
SB1/US47 | Implement Freemium Model Setup | SB1/US2/T3 | Test and validate functionality of implement freemium model setup | aayush pareek | Not Started | 2025-09-19
SB1/US48 | Implement Data Backup | SB1/US3/T1 | Design frontend/backend components for implement data backup | dev choudhary | Not Started | 2025-09-22
SB1/US48 | Implement Data Backup | SB1/US3/T2 | Develop API and integrate database for implement data backup | dev choudhary | Not Started | 2025-09-22
SB1/US48 | Implement Data Backup | SB1/US3/T3 | Test and validate functionality of implement data backup | dev choudhary | Not Started | 2025-09-23
SB1/US49 | Implement Encryption Implementation | SB1/US4/T1 | Design frontend/backend components for implement encryption implementation | rishank jain | Not Started | 2025-09-26
SB1/US49 | Implement Encryption Implementation | SB1/US4/T2 | Develop API and integrate database for implement encryption implementation | rishank jain | Not Started | 2025-09-29
SB1/US49 | Implement Encryption Implementation | SB1/US4/T3 | Test and validate functionality of implement encryption implementation | rishank jain | Not Started | 2025-09-30
SB1/US50 | Implement Premium Subscription Setup | SB1/US5/T1 | Design frontend/backend components for implement premium subscription setup | aayush pareek | Not Started | 2025-09-30
SB1/US50 | Implement Premium Subscription Setup | SB1/US5/T2 | Develop API and integrate database for implement premium subscription setup | aayush pareek | Not Started | 2025-10-09
SB1/US50 | Implement Premium Subscription Setup | SB1/US5/T3 | Test and validate functionality of implement premium subscription setup | aayush pareek | Not Started | 2025-10-10
SB1/US51 | Implement Cloud Integration | SB1/US6/T1 | Design frontend/backend components for implement cloud integration | dev choudhary | Not Started | 2025-10-13
SB1/US51 | Implement Cloud Integration | SB1/US6/T2 | Develop API and integrate database for implement cloud integration | dev choudhary | Not Started | 2025-10-13
SB1/US51 | Implement Cloud Integration | SB1/US6/T3 | Test and validate functionality of implement cloud integration | dev choudhary | Not Started | 2025-10-06
SB1/US52 | Implement Biometric Alive Check | SB1/US7/T1 | Design frontend/backend components for implement biometric alive check | rishank jain | Not Started | 2025-10-07
SB1/US52 | Implement Biometric Alive Check | SB1/US7/T2 | Develop API and integrate database for implement biometric alive check | rishank jain | Not Started | 2025-10-07
SB1/US52 | Implement Biometric Alive Check | SB1/US7/T3 | Test and validate functionality of implement biometric alive check | rishank jain | Not Started | 2025-10-08
SB1/US53 | Implement User Dashboard | SB1/US8/T1 | Design frontend/backend components for implement user dashboard | aayush pareek | Not Started | 2025-10-13
SB1/US53 | Implement User Dashboard | SB1/US8/T2 | Develop API and integrate database for implement user dashboard | aayush pareek | Not Started | 2025-10-14
SB1/US53 | Implement User Dashboard | SB1/US8/T3 | Test and validate functionality of implement user dashboard | aayush pareek | Not Started | 2025-10-14
SB1/US54 | Implement Biometric Alive Check | SB1/US9/T1 | Design frontend/backend components for implement biometric alive check | dev choudhary | Not Started | 2025-10-15
SB1/US54 | Implement Biometric Alive Check | SB1/US9/T2 | Develop API and integrate database for implement biometric alive check | dev choudhary | Not Started | 2025-10-13
SB1/US54 | Implement Biometric Alive Check | SB1/US9/T3 | Test and validate functionality of implement biometric alive check | dev choudhary | Not Started | 2025-10-14
SB1/US55 | Implement Schedule Delivery | SB1/US10/T1 | Design frontend/backend components for implement schedule delivery | rishank jain | Not Started | 2025-10-14
SB1/US55 | Implement Schedule Delivery | SB1/US10/T2 | Develop API and integrate database for implement schedule delivery | rishank jain | Not Started | 2025-10-15
SB1/US55 | Implement Schedule Delivery | SB1/US10/T3 | Test and validate functionality of implement schedule delivery | rishank jain | Not Started | 2025-10-09
SB1/US56 | Implement User Dashboard | SB1/US11/T1 | Design frontend/backend components for implement user dashboard | aayush pareek | Not Started | 2025-10-10
SB1/US56 | Implement User Dashboard | SB1/US11/T2 | Develop API and integrate database for implement user dashboard | aayush pareek | Not Started | 2025-10-13
SB1/US56 | Implement User Dashboard | SB1/US11/T3 | Test and validate functionality of implement user dashboard | aayush pareek | Not Started | 2025-10-13
SB1/US57 | Implement Freemium Model Setup | SB1/US12/T1 | Design frontend/backend components for implement freemium model setup | dev choudhary | Not Started | 2025-10-14
SB1/US57 | Implement Freemium Model Setup | SB1/US12/T2 | Develop API and integrate database for implement freemium model setup | dev choudhary | Not Started | 2025-10-15
SB1/US57 | Implement Freemium Model Setup | SB1/US12/T3 | Test and validate functionality of implement freemium model setup | dev choudhary | Not Started | 2025-10-15
SB1/US58 | Implement Guardian Verification | SB1/US13/T1 | Design frontend/backend components for implement guardian verification | rishank jain | Not Started | 2025-10-16
SB1/US58 | Implement Guardian Verification | SB1/US13/T2 | Develop API and integrate database for implement guardian verification | rishank jain | Not Started | 2025-10-16
SB1/US58 | Implement Guardian Verification | SB1/US13/T3 | Test and validate functionality of implement guardian verification | rishank jain | Not Started | 2025-10-17
SB1/US59 | Implement Premium Subscription Setup | SB1/US14/T1 | Design frontend/backend components for implement premium subscription setup | aayush pareek | Not Started | 2025-10-17
SB1/US59 | Implement Premium Subscription Setup | SB1/US14/T2 | Develop API and integrate database for implement premium subscription setup | aayush pareek | Not Started | 2025-10-20
SB1/US59 | Implement Premium Subscription Setup | SB1/US14/T3 | Test and validate functionality of implement premium subscription setup | aayush pareek | Not Started | 2025-10-15
SB1/US60 | Implement Freemium Model Setup | SB1/US15/T1 | Design frontend/backend components for implement freemium model setup | dev choudhary | Not Started | 2025-10-16
SB1/US60 | Implement Freemium Model Setup | SB1/US15/T2 | Develop API and integrate database for implement freemium model setup | dev choudhary | Not Started | 2025-10-16
SB1/US60 | Implement Freemium Model Setup | SB1/US15/T3 | Test and validate functionality of implement freemium model setup | dev choudhary | Not Started | 2025-10-17
SB1/US61 | Implement Cloud Integration | SB1/US1/T1 | Design frontend/backend components for implement cloud integration | rishank jain | Not Started | 2025-10-17
SB1/US61 | Implement Cloud Integration | SB1/US1/T2 | Develop API and integrate database for implement cloud integration | rishank jain | Not Started | 2025-10-20
SB1/US61 | Implement Cloud Integration | SB1/US1/T3 | Test and validate functionality of implement cloud integration | rishank jain | Not Started | 2025-10-20
SB1/US62 | Implement Blockchain Hashing | SB1/US2/T1 | Design frontend/backend components for implement blockchain hashing | aayush pareek | Not Started | 2025-10-21
SB1/US62 | Implement Blockchain Hashing | SB1/US2/T2 | Develop API and integrate database for implement blockchain hashing | aayush pareek | Not Started | 2025-10-16
SB1/US62 | Implement Blockchain Hashing | SB1/US2/T3 | Test and validate functionality of implement blockchain hashing | aayush pareek | Not Started | 2025-10-17
SB1/US63 | Implement Blockchain Hashing | SB1/US3/T1 | Design frontend/backend components for implement blockchain hashing | dev choudhary | Not Started | 2025-10-17
SB1/US63 | Implement Blockchain Hashing | SB1/US3/T2 | Develop API and integrate database for implement blockchain hashing | dev choudhary | Not Started | 2025-10-20
SB1/US63 | Implement Blockchain Hashing | SB1/US3/T3 | Test and validate functionality of implement blockchain hashing | dev choudhary | Not Started | 2025-09-23
SB1/US64 | Implement Recipient Management | SB1/US4/T1 | Design frontend/backend components for implement recipient management | rishank jain | Not Started | 2025-09-24
SB1/US64 | Implement Recipient Management | SB1/US4/T2 | Develop API and integrate database for implement recipient management | rishank jain | Not Started | 2025-09-25
SB1/US64 | Implement Recipient Management | SB1/US4/T3 | Test and validate functionality of implement recipient management | rishank jain | Not Started | 2025-09-25
SB1/US65 | Implement User Dashboard | SB1/US5/T1 | Design frontend/backend components for implement user dashboard | aayush pareek | Not Started | 2025-09-24
SB1/US65 | Implement User Dashboard | SB1/US5/T2 | Develop API and integrate database for implement user dashboard | aayush pareek | Not Started | 2025-09-25
SB1/US65 | Implement User Dashboard | SB1/US5/T3 | Test and validate functionality of implement user dashboard | aayush pareek | Not Started | 2025-09-25
SB2/US6 | Implement Template Selection | SB2/US6/T1 | Design frontend/backend components for implement template selection | dev choudhary | Not Started | 2025-09-26
SB2/US6 | Implement Template Selection | SB2/US6/T2 | Develop API and integrate database for implement template selection | dev choudhary | Not Started | 2025-10-01
SB2/US6 | Implement Template Selection | SB2/US6/T3 | Test and validate functionality of implement template selection | dev choudhary | Not Started | 2025-10-02
SB2/US7 | Implement Template Selection | SB2/US7/T1 | Design frontend/backend components for implement template selection | rishank jain | Not Started | 2025-10-02
SB2/US7 | Implement Template Selection | SB2/US7/T2 | Develop API and integrate database for implement template selection | rishank jain | Not Started | 2025-10-03
SB2/US7 | Implement Template Selection | SB2/US7/T3 | Test and validate functionality of implement template selection | rishank jain | Not Started | 2025-10-17
SB2/US8 | Implement Legal Compliance | SB2/US8/T1 | Design frontend/backend components for implement legal compliance | aayush pareek | Not Started | 2025-10-20
SB2/US8 | Implement Legal Compliance | SB2/US8/T2 | Develop API and integrate database for implement legal compliance | aayush pareek | Not Started | 2025-10-20
SB2/US8 | Implement Legal Compliance | SB2/US8/T3 | Test and validate functionality of implement legal compliance | aayush pareek | Not Started | 2025-10-21
SB2/US9 | Implement Legal Compliance | SB2/US9/T1 | Design frontend/backend components for implement legal compliance | dev choudhary | Not Started | 2025-10-21
SB2/US9 | Implement Legal Compliance | SB2/US9/T2 | Develop API and integrate database for implement legal compliance | dev choudhary | Not Started | 2025-10-22
SB2/US9 | Implement Legal Compliance | SB2/US9/T3 | Test and validate functionality of implement legal compliance | dev choudhary | Not Started | 2025-10-22
SB2/US10 | Implement Freemium Model Setup | SB2/US10/T1 | Design frontend/backend components for implement freemium model setup | rishank jain | Not Started | 2025-10-23
SB2/US10 | Implement Freemium Model Setup | SB2/US10/T2 | Develop API and integrate database for implement freemium model setup | rishank jain | Not Started | 2025-10-20
SB2/US10 | Implement Freemium Model Setup | SB2/US10/T3 | Test and validate functionality of implement freemium model setup | rishank jain | Not Started | 2025-10-21
SB2/US11 | Implement Create Capsule | SB2/US11/T1 | Design frontend/backend components for implement create capsule | aayush pareek | Not Started | 2025-10-21
SB2/US11 | Implement Create Capsule | SB2/US11/T2 | Develop API and integrate database for implement create capsule | aayush pareek | Not Started | 2025-10-22
SB2/US11 | Implement Create Capsule | SB2/US11/T3 | Test and validate functionality of implement create capsule | aayush pareek | Not Started | 2025-09-24
SB2/US12 | Implement Capsule Preview | SB2/US12/T1 | Design frontend/backend components for implement capsule preview | dev choudhary | Not Started | 2025-09-25
SB2/US12 | Implement Capsule Preview | SB2/US12/T2 | Develop API and integrate database for implement capsule preview | dev choudhary | Not Started | 2025-09-25
SB2/US12 | Implement Capsule Preview | SB2/US12/T3 | Test and validate functionality of implement capsule preview | dev choudhary | Not Started | 2025-09-26
SB2/US13 | Implement Voice/Video Support | SB2/US13/T1 | Design frontend/backend components for implement voice/video support | rishank jain | Not Started | 2025-10-03
SB2/US13 | Implement Voice/Video Support | SB2/US13/T2 | Develop API and integrate database for implement voice/video support | rishank jain | Not Started | 2025-10-06
SB2/US13 | Implement Voice/Video Support | SB2/US13/T3 | Test and validate functionality of implement voice/video support | rishank jain | Not Started | 2025-10-06
SB2/US14 | Implement Capsule Preview | SB2/US14/T1 | Design frontend/backend components for implement capsule preview | aayush pareek | Not Started | 2025-10-07
SB2/US14 | Implement Capsule Preview | SB2/US14/T2 | Develop API and integrate database for implement capsule preview | aayush pareek | Not Started | 2025-10-20
SB2/US14 | Implement Capsule Preview | SB2/US14/T3 | Test and validate functionality of implement capsule preview | aayush pareek | Not Started | 2025-10-21
SB2/US15 | Implement Notification System | SB2/US15/T1 | Design frontend/backend components for implement notification system | dev choudhary | Not Started | 2025-10-22
SB2/US15 | Implement Notification System | SB2/US15/T2 | Develop API and integrate database for implement notification system | dev choudhary | Not Started | 2025-10-22
SB2/US15 | Implement Notification System | SB2/US15/T3 | Test and validate functionality of implement notification system | dev choudhary | Not Started | 2025-10-23
SB2/US1 | Implement Role Management | SB2/US1/T1 | Design frontend/backend components for implement role management | rishank jain | Not Started | 2025-10-24
SB2/US1 | Implement Role Management | SB2/US1/T2 | Develop API and integrate database for implement role management | rishank jain | Not Started | 2025-10-24
SB2/US1 | Implement Role Management | SB2/US1/T3 | Test and validate functionality of implement role management | rishank jain | Not Started | 2025-10-27
SB2/US2 | Implement Data Backup | SB2/US2/T1 | Design frontend/backend components for implement data backup | aayush pareek | Not Started | 2025-10-23
SB2/US2 | Implement Data Backup | SB2/US2/T2 | Develop API and integrate database for implement data backup | aayush pareek | Not Started | 2025-10-24
SB2/US2 | Implement Data Backup | SB2/US2/T3 | Test and validate functionality of implement data backup | aayush pareek | Not Started | 2025-10-24
SB2/US3 | Implement Notification System | SB2/US3/T1 | Design frontend/backend components for implement notification system | dev choudhary | Not Started | 2025-10-27
SB2/US3 | Implement Notification System | SB2/US3/T2 | Develop API and integrate database for implement notification system | dev choudhary | Not Started | 2025-10-22
SB2/US3 | Implement Notification System | SB2/US3/T3 | Test and validate functionality of implement notification system | dev choudhary | Not Started | 2025-10-23
SB2/US4 | Implement Legal Compliance | SB2/US4/T1 | Design frontend/backend components for implement legal compliance | rishank jain | Not Started | 2025-10-23
SB2/US4 | Implement Legal Compliance | SB2/US4/T2 | Develop API and integrate database for implement legal compliance | rishank jain | Not Started | 2025-10-24
SB2/US4 | Implement Legal Compliance | SB2/US4/T3 | Test and validate functionality of implement legal compliance | rishank jain | Not Started | 2025-10-27
SB2/US5 | Implement Recipient Management | SB2/US5/T1 | Design frontend/backend components for implement recipient management | aayush pareek | Not Started | 2025-10-28
SB2/US5 | Implement Recipient Management | SB2/US5/T2 | Develop API and integrate database for implement recipient management | aayush pareek | Not Started | 2025-10-28
SB2/US5 | Implement Recipient Management | SB2/US5/T3 | Test and validate functionality of implement recipient management | aayush pareek | Not Started | 2025-10-29
SB2/US6 | Implement Biometric Alive Check | SB2/US6/T1 | Design frontend/backend components for implement biometric alive check | dev choudhary | Not Started | 2025-10-23
SB2/US6 | Implement Biometric Alive Check | SB2/US6/T2 | Develop API and integrate database for implement biometric alive check | dev choudhary | Not Started | 2025-10-24
SB2/US6 | Implement Biometric Alive Check | SB2/US6/T3 | Test and validate functionality of implement biometric alive check | dev choudhary | Not Started | 2025-10-27
SB2/US7 | Implement Create Capsule | SB2/US7/T1 | Design frontend/backend components for implement create capsule | rishank jain | Not Started | 2025-10-27
SB2/US7 | Implement Create Capsule | SB2/US7/T2 | Develop API and integrate database for implement create capsule | rishank jain | Not Started | 2025-10-28
SB2/US7 | Implement Create Capsule | SB2/US7/T3 | Test and validate functionality of implement create capsule | rishank jain | Not Started | 2025-10-29
SB2/US8 | Implement Biometric Alive Check | SB2/US8/T1 | Design frontend/backend components for implement biometric alive check | aayush pareek | Not Started | 2025-10-29
SB2/US8 | Implement Biometric Alive Check | SB2/US8/T2 | Develop API and integrate database for implement biometric alive check | aayush pareek | Not Started | 2025-10-30
SB2/US8 | Implement Biometric Alive Check | SB2/US8/T3 | Test and validate functionality of implement biometric alive check | aayush pareek | Not Started | 2025-09-10

## sprint 2
SPRINT BACKLOG 2
US ID | USER STORY | TASK ID | TASKS | TM | STATUS (NOT STARTED / IN PROGRESS / COMPLETED) | ESTIMATED DATE OF TASK COMPLETION
SPRINT 1 - <Digital College>
SB2/US1 | Implement Template Selection | SB2/US6/T1 | Design frontend/backend components for implement template selection | rishank jain | Not Started | 2025-09-10
SB2/US1 | Implement Template Selection | SB2/US6/T2 | Develop API and integrate database for implement template selection | rishank jain | Not Started | 2025-09-10
SB2/US1 | Implement Template Selection | SB2/US6/T3 | Test and validate functionality of implement template selection | rishank jain | Not Started | 2025-09-11
SB2/US2 | Implement Template Selection | SB2/US7/T1 | Design frontend/backend components for implement template selection | aayush pareek | Not Started | 2025-09-11
SB2/US2 | Implement Template Selection | SB2/US7/T2 | Develop API and integrate database for implement template selection | aayush pareek | Not Started | 2025-09-10
SB2/US2 | Implement Template Selection | SB2/US7/T3 | Test and validate functionality of implement template selection | aayush pareek | Not Started | 2025-09-11
SB2/US3 | Implement Legal Compliance | SB2/US8/T1 | Design frontend/backend components for implement legal compliance | dev choudhary | Not Started | 2025-09-11
SB2/US3 | Implement Legal Compliance | SB2/US8/T2 | Develop API and integrate database for implement legal compliance | dev choudhary | Not Started | 2025-09-12
SB2/US3 | Implement Legal Compliance | SB2/US8/T3 | Test and validate functionality of implement legal compliance | dev choudhary | Not Started | 2025-09-12
SB2/US4 | Implement Legal Compliance | SB2/US9/T1 | Design frontend/backend components for implement legal compliance | rishank jain | Not Started | 2025-09-12
SB2/US4 | Implement Legal Compliance | SB2/US9/T2 | Develop API and integrate database for implement legal compliance | rishank jain | Not Started | 2025-09-15
SB2/US4 | Implement Legal Compliance | SB2/US9/T3 | Test and validate functionality of implement legal compliance | rishank jain | Not Started | 2025-09-15
SB2/US5 | Implement Freemium Model Setup | SB2/US10/T1 | Design frontend/backend components for implement freemium model setup | aayush pareek | Not Started | 2025-09-15
SB2/US5 | Implement Freemium Model Setup | SB2/US10/T2 | Develop API and integrate database for implement freemium model setup | aayush pareek | Not Started | 2025-09-16
SB2/US5 | Implement Freemium Model Setup | SB2/US10/T3 | Test and validate functionality of implement freemium model setup | aayush pareek | Not Started | 2025-09-16
SB2/US6 | Implement Create Capsule | SB2/US11/T1 | Design frontend/backend components for implement create capsule | dev choudhary | Not Started | 2025-09-17
SB2/US6 | Implement Create Capsule | SB2/US11/T2 | Develop API and integrate database for implement create capsule | dev choudhary | Not Started | 2025-09-16
SB2/US6 | Implement Create Capsule | SB2/US11/T3 | Test and validate functionality of implement create capsule | dev choudhary | Not Started | 2025-09-17
SB2/US7 | Implement Capsule Preview | SB2/US12/T1 | Design frontend/backend components for implement capsule preview | rishank jain | Not Started | 2025-09-17
SB2/US7 | Implement Capsule Preview | SB2/US12/T2 | Develop API and integrate database for implement capsule preview | rishank jain | Not Started | 2025-09-18
SB2/US7 | Implement Capsule Preview | SB2/US12/T3 | Test and validate functionality of implement capsule preview | rishank jain | Not Started | 2025-09-18
SB2/US8 | Implement Voice/Video Support | SB2/US13/T1 | Design frontend/backend components for implement voice/video support | aayush pareek | Not Started | 2025-09-19
SB2/US8 | Implement Voice/Video Support | SB2/US13/T2 | Develop API and integrate database for implement voice/video support | aayush pareek | Not Started | 2025-09-22
SB2/US8 | Implement Voice/Video Support | SB2/US13/T3 | Test and validate functionality of implement voice/video support | aayush pareek | Not Started | 2025-09-22
SB2/US9 | Implement Capsule Preview | SB2/US14/T1 | Design frontend/backend components for implement capsule preview | dev choudhary | Not Started | 2025-09-12
SB2/US9 | Implement Capsule Preview | SB2/US14/T2 | Develop API and integrate database for implement capsule preview | dev choudhary | Not Started | 2025-09-15
SB2/US9 | Implement Capsule Preview | SB2/US14/T3 | Test and validate functionality of implement capsule preview | dev choudhary | Not Started | 2025-09-16
SB2/US10 | Implement Notification System | SB2/US15/T1 | Design frontend/backend components for implement notification system | rishank jain | Not Started | 2025-09-16
SB2/US10 | Implement Notification System | SB2/US15/T2 | Develop API and integrate database for implement notification system | rishank jain | Not Started | 2025-09-23
SB2/US10 | Implement Notification System | SB2/US15/T3 | Test and validate functionality of implement notification system | rishank jain | Not Started | 2025-09-24
SB2/US11 | Implement Role Management | SB2/US1/T1 | Design frontend/backend components for implement role management | aayush pareek | Not Started | 2025-09-24
SB2/US11 | Implement Role Management | SB2/US1/T2 | Develop API and integrate database for implement role management | aayush pareek | Not Started | 2025-09-25
SB2/US11 | Implement Role Management | SB2/US1/T3 | Test and validate functionality of implement role management | aayush pareek | Not Started | 2025-09-25
SB2/US12 | Implement Data Backup | SB2/US2/T1 | Design frontend/backend components for implement data backup | dev choudhary | Not Started | 2025-09-26
SB2/US12 | Implement Data Backup | SB2/US2/T2 | Develop API and integrate database for implement data backup | dev choudhary | Not Started | 2025-09-26
SB2/US12 | Implement Data Backup | SB2/US2/T3 | Test and validate functionality of implement data backup | dev choudhary | Not Started | 2025-09-29
SB2/US13 | Implement Notification System | SB2/US3/T1 | Design frontend/backend components for implement notification system | rishank jain | Not Started | 2025-09-23
SB2/US13 | Implement Notification System | SB2/US3/T2 | Develop API and integrate database for implement notification system | rishank jain | Not Started | 2025-09-24
SB2/US13 | Implement Notification System | SB2/US3/T3 | Test and validate functionality of implement notification system | rishank jain | Not Started | 2025-09-25
SB2/US14 | Implement Legal Compliance | SB2/US4/T1 | Design frontend/backend components for implement legal compliance | aayush pareek | Not Started | 2025-09-25
SB2/US14 | Implement Legal Compliance | SB2/US4/T2 | Develop API and integrate database for implement legal compliance | aayush pareek | Not Started | 2025-09-29
SB2/US14 | Implement Legal Compliance | SB2/US4/T3 | Test and validate functionality of implement legal compliance | aayush pareek | Not Started | 2025-09-30
SB2/US15 | Implement Recipient Management | SB2/US5/T1 | Design frontend/backend components for implement recipient management | dev choudhary | Not Started | 2025-09-30
SB2/US15 | Implement Recipient Management | SB2/US5/T2 | Develop API and integrate database for implement recipient management | dev choudhary | Not Started | 2025-10-01
SB2/US15 | Implement Recipient Management | SB2/US5/T3 | Test and validate functionality of implement recipient management | dev choudhary | Not Started | 2025-10-02
SB2/US16 | Implement Biometric Alive Check | SB2/US6/T1 | Design frontend/backend components for implement biometric alive check | rishank jain | Not Started | 2025-10-03
SB2/US16 | Implement Biometric Alive Check | SB2/US6/T2 | Develop API and integrate database for implement biometric alive check | rishank jain | Not Started | 2025-10-03
SB2/US16 | Implement Biometric Alive Check | SB2/US6/T3 | Test and validate functionality of implement biometric alive check | rishank jain | Not Started | 2025-10-06
SB2/US17 | Implement Create Capsule | SB2/US7/T1 | Design frontend/backend components for implement create capsule | aayush pareek | Not Started | 2025-09-18
SB2/US17 | Implement Create Capsule | SB2/US7/T2 | Develop API and integrate database for implement create capsule | aayush pareek | Not Started | 2025-09-19
SB2/US17 | Implement Create Capsule | SB2/US7/T3 | Test and validate functionality of implement create capsule | aayush pareek | Not Started | 2025-09-22
SB2/US18 | Implement Biometric Alive Check | SB2/US8/T1 | Design frontend/backend components for implement biometric alive check | dev choudhary | Not Started | 2025-09-22
SB2/US18 | Implement Biometric Alive Check | SB2/US8/T2 | Develop API and integrate database for implement biometric alive check | dev choudhary | Not Started | 2025-10-02
SB2/US18 | Implement Biometric Alive Check | SB2/US8/T3 | Test and validate functionality of implement biometric alive check | dev choudhary | Not Started | 2025-10-03
SB2/US19 | Implement Event Triggering | SB2/US9/T1 | Design frontend/backend components for implement event triggering | rishank jain | Not Started | 2025-10-06
SB2/US19 | Implement Event Triggering | SB2/US9/T2 | Develop API and integrate database for implement event triggering | rishank jain | Not Started | 2025-10-06
SB2/US19 | Implement Event Triggering | SB2/US9/T3 | Test and validate functionality of implement event triggering | rishank jain | Not Started | 2025-09-29
SB2/US20 | Implement Role Management | SB2/US10/T1 | Design frontend/backend components for implement role management | aayush pareek | Not Started | 2025-09-30
SB2/US20 | Implement Role Management | SB2/US10/T2 | Develop API and integrate database for implement role management | aayush pareek | Not Started | 2025-10-01
SB2/US20 | Implement Role Management | SB2/US10/T3 | Test and validate functionality of implement role management | aayush pareek | Not Started | 2025-10-02
SB2/US21 | Implement Guardian Verification | SB2/US11/T1 | Design frontend/backend components for implement guardian verification | dev choudhary | Not Started | 2025-10-07
SB2/US21 | Implement Guardian Verification | SB2/US11/T2 | Develop API and integrate database for implement guardian verification | dev choudhary | Not Started | 2025-10-08
SB2/US21 | Implement Guardian Verification | SB2/US11/T3 | Test and validate functionality of implement guardian verification | dev choudhary | Not Started | 2025-10-08
SB2/US22 | Implement Blockchain Hashing | SB2/US12/T1 | Design frontend/backend components for implement blockchain hashing | rishank jain | Not Started | 2025-10-09
SB2/US22 | Implement Blockchain Hashing | SB2/US12/T2 | Develop API and integrate database for implement blockchain hashing | rishank jain | Not Started | 2025-09-17
SB2/US22 | Implement Blockchain Hashing | SB2/US12/T3 | Test and validate functionality of implement blockchain hashing | rishank jain | Not Started | 2025-09-18
SB2/US23 | Implement Blockchain Hashing | SB2/US13/T1 | Design frontend/backend components for implement blockchain hashing | aayush pareek | Not Started | 2025-09-18
SB2/US23 | Implement Blockchain Hashing | SB2/US13/T2 | Develop API and integrate database for implement blockchain hashing | aayush pareek | Not Started | 2025-09-19
SB2/US23 | Implement Blockchain Hashing | SB2/US13/T3 | Test and validate functionality of implement blockchain hashing | aayush pareek | Not Started | 2025-09-17
SB2/US24 | Implement Notification System | SB2/US14/T1 | Design frontend/backend components for implement notification system | dev choudhary | Not Started | 2025-09-18
SB2/US24 | Implement Notification System | SB2/US14/T2 | Develop API and integrate database for implement notification system | dev choudhary | Not Started | 2025-09-19
SB2/US24 | Implement Notification System | SB2/US14/T3 | Test and validate functionality of implement notification system | dev choudhary | Not Started | 2025-09-19
SB2/US25 | Implement Role Management | SB2/US15/T1 | Design frontend/backend components for implement role management | rishank jain | Not Started | 2025-10-01
SB2/US25 | Implement Role Management | SB2/US15/T2 | Develop API and integrate database for implement role management | rishank jain | Not Started | 2025-10-02
SB2/US25 | Implement Role Management | SB2/US15/T3 | Test and validate functionality of implement role management | rishank jain | Not Started | 2025-10-02
SB2/US26 | Implement Create Capsule | SB2/US1/T1 | Design frontend/backend components for implement create capsule | aayush pareek | Not Started | 2025-10-03
SB2/US26 | Implement Create Capsule | SB2/US1/T2 | Develop API and integrate database for implement create capsule | aayush pareek | Not Started | 2025-10-06
SB2/US26 | Implement Create Capsule | SB2/US1/T3 | Test and validate functionality of implement create capsule | aayush pareek | Not Started | 2025-10-07
SB2/US27 | Implement Role Management | SB2/US2/T1 | Design frontend/backend components for implement role management | dev choudhary | Not Started | 2025-10-07
SB2/US27 | Implement Role Management | SB2/US2/T2 | Develop API and integrate database for implement role management | dev choudhary | Not Started | 2025-10-08
SB2/US27 | Implement Role Management | SB2/US2/T3 | Test and validate functionality of implement role management | dev choudhary | Not Started | 2025-10-07
SB2/US28 | Implement Upload Media | SB2/US3/T1 | Design frontend/backend components for implement upload media | rishank jain | Not Started | 2025-10-08
SB2/US28 | Implement Upload Media | SB2/US3/T2 | Develop API and integrate database for implement upload media | rishank jain | Not Started | 2025-10-08
SB2/US28 | Implement Upload Media | SB2/US3/T3 | Test and validate functionality of implement upload media | rishank jain | Not Started | 2025-10-09
SB2/US29 | Implement Cloud Integration | SB2/US4/T1 | Design frontend/backend components for implement cloud integration | aayush pareek | Not Started | 2025-09-23
SB2/US29 | Implement Cloud Integration | SB2/US4/T2 | Develop API and integrate database for implement cloud integration | aayush pareek | Not Started | 2025-09-24
SB2/US29 | Implement Cloud Integration | SB2/US4/T3 | Test and validate functionality of implement cloud integration | aayush pareek | Not Started | 2025-09-24
SB2/US30 | Implement Create Capsule | SB2/US5/T1 | Design frontend/backend components for implement create capsule | dev choudhary | Not Started | 2025-09-25
SB2/US30 | Implement Create Capsule | SB2/US5/T2 | Develop API and integrate database for implement create capsule | dev choudhary | Not Started | 2025-09-12
SB2/US30 | Implement Create Capsule | SB2/US5/T3 | Test and validate functionality of implement create capsule | dev choudhary | Not Started | 2025-09-15
SB2/US31 | Implement Recipient Management | SB2/US6/T1 | Design frontend/backend components for implement recipient management | rishank jain | Not Started | 2025-09-15
SB2/US31 | Implement Recipient Management | SB2/US6/T2 | Develop API and integrate database for implement recipient management | rishank jain | Not Started | 2025-09-16
SB2/US31 | Implement Recipient Management | SB2/US6/T3 | Test and validate functionality of implement recipient management | rishank jain | Not Started | 2025-09-26
SB2/US32 | Implement Capsule Preview | SB2/US7/T1 | Design frontend/backend components for implement capsule preview | aayush pareek | Not Started | 2025-09-29
SB2/US32 | Implement Capsule Preview | SB2/US7/T2 | Develop API and integrate database for implement capsule preview | aayush pareek | Not Started | 2025-09-29
SB2/US32 | Implement Capsule Preview | SB2/US7/T3 | Test and validate functionality of implement capsule preview | aayush pareek | Not Started | 2025-09-30
SB2/US33 | Implement Role Management | SB2/US8/T1 | Design frontend/backend components for implement role management | dev choudhary | Not Started | 2025-10-01
SB2/US33 | Implement Role Management | SB2/US8/T2 | Develop API and integrate database for implement role management | dev choudhary | Not Started | 2025-10-02
SB2/US33 | Implement Role Management | SB2/US8/T3 | Test and validate functionality of implement role management | dev choudhary | Not Started | 2025-10-02
SB2/US34 | Implement Cloud Integration | SB2/US9/T1 | Design frontend/backend components for implement cloud integration | rishank jain | Not Started | 2025-10-03
SB2/US34 | Implement Cloud Integration | SB2/US9/T2 | Develop API and integrate database for implement cloud integration | rishank jain | Not Started | 2025-09-12
SB2/US34 | Implement Cloud Integration | SB2/US9/T3 | Test and validate functionality of implement cloud integration | rishank jain | Not Started | 2025-09-15
SB2/US35 | Implement Guardian Verification | SB2/US10/T1 | Design frontend/backend components for implement guardian verification | aayush pareek | Not Started | 2025-09-15
SB2/US35 | Implement Guardian Verification | SB2/US10/T2 | Develop API and integrate database for implement guardian verification | aayush pareek | Not Started | 2025-09-16
SB2/US35 | Implement Guardian Verification | SB2/US10/T3 | Test and validate functionality of implement guardian verification | aayush pareek | Not Started | 2025-10-07
SB2/US36 | Implement Role Management | SB2/US11/T1 | Design frontend/backend components for implement role management | dev choudhary | Not Started | 2025-10-08
SB2/US36 | Implement Role Management | SB2/US11/T2 | Develop API and integrate database for implement role management | dev choudhary | Not Started | 2025-10-08
SB2/US36 | Implement Role Management | SB2/US11/T3 | Test and validate functionality of implement role management | dev choudhary | Not Started | 2025-10-09
SB2/US37 | Implement Role Management | SB2/US12/T1 | Design frontend/backend components for implement role management | rishank jain | Not Started | 2025-10-02
SB2/US37 | Implement Role Management | SB2/US12/T2 | Develop API and integrate database for implement role management | rishank jain | Not Started | 2025-10-03
SB2/US37 | Implement Role Management | SB2/US12/T3 | Test and validate functionality of implement role management | rishank jain | Not Started | 2025-10-03
SB2/US38 | Implement Upload Media | SB2/US13/T1 | Design frontend/backend components for implement upload media | aayush pareek | Not Started | 2025-10-06
SB2/US38 | Implement Upload Media | SB2/US13/T2 | Develop API and integrate database for implement upload media | aayush pareek | Not Started | 2025-09-17
SB2/US38 | Implement Upload Media | SB2/US13/T3 | Test and validate functionality of implement upload media | aayush pareek | Not Started | 2025-09-18
SB2/US39 | Implement Blockchain Hashing | SB2/US14/T1 | Design frontend/backend components for implement blockchain hashing | dev choudhary | Not Started | 2025-09-18
SB2/US39 | Implement Blockchain Hashing | SB2/US14/T2 | Develop API and integrate database for implement blockchain hashing | dev choudhary | Not Started | 2025-09-19
SB2/US39 | Implement Blockchain Hashing | SB2/US14/T3 | Test and validate functionality of implement blockchain hashing | dev choudhary | Not Started | 2025-09-19
SB2/US40 | Implement Blockchain Hashing | SB2/US15/T1 | Design frontend/backend components for implement blockchain hashing | rishank jain | Not Started | 2025-09-22
SB2/US40 | Implement Blockchain Hashing | SB2/US15/T2 | Develop API and integrate database for implement blockchain hashing | rishank jain | Not Started | 2025-09-23
SB2/US40 | Implement Blockchain Hashing | SB2/US15/T3 | Test and validate functionality of implement blockchain hashing | rishank jain | Not Started | 2025-09-23
SB2/US41 | Implement Upload Media | SB2/US1/T1 | Design frontend/backend components for implement upload media | aayush pareek | Not Started | 2025-09-23
SB2/US41 | Implement Upload Media | SB2/US1/T2 | Develop API and integrate database for implement upload media | aayush pareek | Not Started | 2025-09-24
SB2/US41 | Implement Upload Media | SB2/US1/T3 | Test and validate functionality of implement upload media | aayush pareek | Not Started | 2025-09-24
SB2/US42 | Implement Guardian Verification | SB2/US2/T1 | Design frontend/backend components for implement guardian verification | dev choudhary | Not Started | 2025-09-25
SB2/US42 | Implement Guardian Verification | SB2/US2/T2 | Develop API and integrate database for implement guardian verification | dev choudhary | Not Started | 2025-09-25
SB2/US42 | Implement Guardian Verification | SB2/US2/T3 | Test and validate functionality of implement guardian verification | dev choudhary | Not Started | 2025-09-26
SB2/US43 | Implement Capsule Preview | SB2/US3/T1 | Design frontend/backend components for implement capsule preview | rishank jain | Not Started | 2025-09-29
SB2/US43 | Implement Capsule Preview | SB2/US3/T2 | Develop API and integrate database for implement capsule preview | rishank jain | Not Started | 2025-09-29
SB2/US43 | Implement Capsule Preview | SB2/US3/T3 | Test and validate functionality of implement capsule preview | rishank jain | Not Started | 2025-10-06
SB2/US44 | Implement Blockchain Hashing | SB2/US4/T1 | Design frontend/backend components for implement blockchain hashing | aayush pareek | Not Started | 2025-10-07
SB2/US44 | Implement Blockchain Hashing | SB2/US4/T2 | Develop API and integrate database for implement blockchain hashing | aayush pareek | Not Started | 2025-10-07
SB2/US44 | Implement Blockchain Hashing | SB2/US4/T3 | Test and validate functionality of implement blockchain hashing | aayush pareek | Not Started | 2025-10-08
SB2/US45 | Implement Create Capsule | SB2/US5/T1 | Design frontend/backend components for implement create capsule | dev choudhary | Not Started | 2025-10-09
SB2/US45 | Implement Create Capsule | SB2/US5/T2 | Develop API and integrate database for implement create capsule | dev choudhary | Not Started | 2025-10-10
SB2/US45 | Implement Create Capsule | SB2/US5/T3 | Test and validate functionality of implement create capsule | dev choudhary | Not Started | 2025-10-10
SB2/US46 | Implement Data Backup | SB2/US6/T1 | Design frontend/backend components for implement data backup | rishank jain | Not Started | 2025-10-13
SB2/US46 | Implement Data Backup | SB2/US6/T2 | Develop API and integrate database for implement data backup | rishank jain | Not Started | 2025-10-09
SB2/US46 | Implement Data Backup | SB2/US6/T3 | Test and validate functionality of implement data backup | rishank jain | Not Started | 2025-10-10
SB2/US47 | Implement Cloud Integration | SB2/US7/T1 | Design frontend/backend components for implement cloud integration | aayush pareek | Not Started | 2025-10-10
SB2/US47 | Implement Cloud Integration | SB2/US7/T2 | Develop API and integrate database for implement cloud integration | aayush pareek | Not Started | 2025-10-13
SB2/US47 | Implement Cloud Integration | SB2/US7/T3 | Test and validate functionality of implement cloud integration | aayush pareek | Not Started | 2025-09-19
SB2/US48 | Implement Create Capsule | SB2/US8/T1 | Design frontend/backend components for implement create capsule | dev choudhary | Not Started | 2025-09-22
SB2/US48 | Implement Create Capsule | SB2/US8/T2 | Develop API and integrate database for implement create capsule | dev choudhary | Not Started | 2025-09-22
SB2/US48 | Implement Create Capsule | SB2/US8/T3 | Test and validate functionality of implement create capsule | dev choudhary | Not Started | 2025-09-23
SB2/US49 | Implement Capsule Preview | SB2/US9/T1 | Design frontend/backend components for implement capsule preview | rishank jain | Not Started | 2025-09-26
SB2/US49 | Implement Capsule Preview | SB2/US9/T2 | Develop API and integrate database for implement capsule preview | rishank jain | Not Started | 2025-09-29
SB2/US49 | Implement Capsule Preview | SB2/US9/T3 | Test and validate functionality of implement capsule preview | rishank jain | Not Started | 2025-09-30
SB2/US50 | Implement Blockchain Hashing | SB2/US10/T1 | Design frontend/backend components for implement blockchain hashing | aayush pareek | Not Started | 2025-09-30
SB2/US50 | Implement Blockchain Hashing | SB2/US10/T2 | Develop API and integrate database for implement blockchain hashing | aayush pareek | Not Started | 2025-10-09
SB2/US50 | Implement Blockchain Hashing | SB2/US10/T3 | Test and validate functionality of implement blockchain hashing | aayush pareek | Not Started | 2025-10-10
SB2/US51 | Implement Legal Compliance | SB2/US11/T1 | Design frontend/backend components for implement legal compliance | dev choudhary | Not Started | 2025-10-13
SB2/US51 | Implement Legal Compliance | SB2/US11/T2 | Develop API and integrate database for implement legal compliance | dev choudhary | Not Started | 2025-10-13
SB2/US51 | Implement Legal Compliance | SB2/US11/T3 | Test and validate functionality of implement legal compliance | dev choudhary | Not Started | 2025-10-06
SB2/US52 | Implement Upload Media | SB2/US12/T1 | Design frontend/backend components for implement upload media | rishank jain | Not Started | 2025-10-07
SB2/US52 | Implement Upload Media | SB2/US12/T2 | Develop API and integrate database for implement upload media | rishank jain | Not Started | 2025-10-07
SB2/US52 | Implement Upload Media | SB2/US12/T3 | Test and validate functionality of implement upload media | rishank jain | Not Started | 2025-10-08
SB2/US53 | Implement Premium Subscription Setup | SB2/US13/T1 | Design frontend/backend components for implement premium subscription setup | aayush pareek | Not Started | 2025-10-13
SB2/US53 | Implement Premium Subscription Setup | SB2/US13/T2 | Develop API and integrate database for implement premium subscription setup | aayush pareek | Not Started | 2025-10-14
SB2/US53 | Implement Premium Subscription Setup | SB2/US13/T3 | Test and validate functionality of implement premium subscription setup | aayush pareek | Not Started | 2025-10-14
SB2/US54 | Implement Encryption Implementation | SB2/US14/T1 | Design frontend/backend components for implement encryption implementation | dev choudhary | Not Started | 2025-10-15
SB2/US54 | Implement Encryption Implementation | SB2/US14/T2 | Develop API and integrate database for implement encryption implementation | dev choudhary | Not Started | 2025-10-13
SB2/US54 | Implement Encryption Implementation | SB2/US14/T3 | Test and validate functionality of implement encryption implementation | dev choudhary | Not Started | 2025-10-14
SB2/US55 | Implement Voice/Video Support | SB2/US15/T1 | Design frontend/backend components for implement voice/video support | rishank jain | Not Started | 2025-10-14
SB2/US55 | Implement Voice/Video Support | SB2/US15/T2 | Develop API and integrate database for implement voice/video support | rishank jain | Not Started | 2025-10-15
SB2/US55 | Implement Voice/Video Support | SB2/US15/T3 | Test and validate functionality of implement voice/video support | rishank jain | Not Started | 2025-10-09
SB2/US56 | Implement Biometric Alive Check | SB2/US1/T1 | Design frontend/backend components for implement biometric alive check | aayush pareek | Not Started | 2025-10-10
SB2/US56 | Implement Biometric Alive Check | SB2/US1/T2 | Develop API and integrate database for implement biometric alive check | aayush pareek | Not Started | 2025-10-13
SB2/US56 | Implement Biometric Alive Check | SB2/US1/T3 | Test and validate functionality of implement biometric alive check | aayush pareek | Not Started | 2025-10-13
SB2/US57 | Implement Data Backup | SB2/US2/T1 | Design frontend/backend components for implement data backup | dev choudhary | Not Started | 2025-10-14
SB2/US57 | Implement Data Backup | SB2/US2/T2 | Develop API and integrate database for implement data backup | dev choudhary | Not Started | 2025-10-15
SB2/US57 | Implement Data Backup | SB2/US2/T3 | Test and validate functionality of implement data backup | dev choudhary | Not Started | 2025-10-15
SB2/US58 | Implement Notification System | SB2/US3/T1 | Design frontend/backend components for implement notification system | rishank jain | Not Started | 2025-10-16
SB2/US58 | Implement Notification System | SB2/US3/T2 | Develop API and integrate database for implement notification system | rishank jain | Not Started | 2025-10-16
SB2/US58 | Implement Notification System | SB2/US3/T3 | Test and validate functionality of implement notification system | rishank jain | Not Started | 2025-10-17
SB2/US59 | Implement Event Triggering | SB2/US4/T1 | Design frontend/backend components for implement event triggering | aayush pareek | Not Started | 2025-10-17
SB2/US59 | Implement Event Triggering | SB2/US4/T2 | Develop API and integrate database for implement event triggering | aayush pareek | Not Started | 2025-10-20
SB2/US59 | Implement Event Triggering | SB2/US4/T3 | Test and validate functionality of implement event triggering | aayush pareek | Not Started | 2025-10-15
SB2/US60 | Implement Create Capsule | SB2/US5/T1 | Design frontend/backend components for implement create capsule | dev choudhary | Not Started | 2025-10-16
SB2/US60 | Implement Create Capsule | SB2/US5/T2 | Develop API and integrate database for implement create capsule | dev choudhary | Not Started | 2025-10-16
SB2/US60 | Implement Create Capsule | SB2/US5/T3 | Test and validate functionality of implement create capsule | dev choudhary | Not Started | 2025-10-17
SB2/US61 | Implement Voice/Video Support | SB2/US6/T1 | Design frontend/backend components for implement voice/video support | rishank jain | Not Started | 2025-10-17
SB2/US61 | Implement Voice/Video Support | SB2/US6/T2 | Develop API and integrate database for implement voice/video support | rishank jain | Not Started | 2025-10-20
SB2/US61 | Implement Voice/Video Support | SB2/US6/T3 | Test and validate functionality of implement voice/video support | rishank jain | Not Started | 2025-10-20
SB2/US62 | Implement Capsule Preview | SB2/US7/T1 | Design frontend/backend components for implement capsule preview | aayush pareek | Not Started | 2025-10-21
SB2/US62 | Implement Capsule Preview | SB2/US7/T2 | Develop API and integrate database for implement capsule preview | aayush pareek | Not Started | 2025-10-16
SB2/US62 | Implement Capsule Preview | SB2/US7/T3 | Test and validate functionality of implement capsule preview | aayush pareek | Not Started | 2025-10-17
SB2/US63 | Implement Data Backup | SB2/US8/T1 | Design frontend/backend components for implement data backup | dev choudhary | Not Started | 2025-10-17
SB2/US63 | Implement Data Backup | SB2/US8/T2 | Develop API and integrate database for implement data backup | dev choudhary | Not Started | 2025-10-20
SB2/US63 | Implement Data Backup | SB2/US8/T3 | Test and validate functionality of implement data backup | dev choudhary | Not Started | 2025-09-23
SB2/US64 | Implement Schedule Delivery | SB2/US9/T1 | Design frontend/backend components for implement schedule delivery | rishank jain | Not Started | 2025-09-24
SB2/US64 | Implement Schedule Delivery | SB2/US9/T2 | Develop API and integrate database for implement schedule delivery | rishank jain | Not Started | 2025-09-25
SB2/US64 | Implement Schedule Delivery | SB2/US9/T3 | Test and validate functionality of implement schedule delivery | rishank jain | Not Started | 2025-09-25
SB2/US65 | Implement Biometric Alive Check | SB2/US10/T1 | Design frontend/backend components for implement biometric alive check | aayush pareek | Not Started | 2025-09-24
SB2/US65 | Implement Biometric Alive Check | SB2/US10/T2 | Develop API and integrate database for implement biometric alive check | aayush pareek | Not Started | 2025-09-25
SB2/US65 | Implement Biometric Alive Check | SB2/US10/T3 | Test and validate functionality of implement biometric alive check | aayush pareek | Not Started | 2025-09-25